## query - 2025-12-03T112713.616
Stnum | Stname | Sq. Ft. | Plan | Subdivision | Lot | Block | Foreman Stage | Stage Completion Percentage | Sold/Available | In Accounting | Open Title | Edwards Co. | Start Date | Interim | Perm | Financing | Buyers Nm | Execution Date | EC Date | E.M. | Ph Number | SP | CS | WIP | L.O. | Agent | Agent Assist | Completion | Foreman
11110 | Ground Cherry | 1825 | Ariana | Campo Del Sol U-1B | 6 | 3 | 40 Ready for Walk-Through | 100% | Model | TRUE | FALSE | Edward's LLC. | 2023-06-05 07:00 | West Star Bank | [7 empty] | 325950 | D | TRUE |  |  |  | 2023-09-18 07:00 | Josue Hinojos
11114 | Ground Cherry | 1879 | Hailey | Campo Del Sol U-1B | 7 | 3 | 40 Ready for Walk-Through | 100% | Model | TRUE | FALSE | Edward's LLC. | 2023-06-05 07:00 | West Star Bank | [7 empty] | 335950 | C | TRUE |  |  |  | 2023-09-18 07:00 | Josue Hinojos
13380 | Emerald Copper | 1833 | Ariana (GK) | Emerald Park U-5 | 18 | 15 | 28 Cabinets | 70% | Available | TRUE | FALSE | Edward's LLC. |  | West Star Bank | [8 empty] | Done | TRUE |  |  |  |  | Samuel Velasco
13384 | Emerald Copper | 1860 | Clarissa (GK) | Emerald Park U-5 | 17 | 15 | 28 Cabinets | 70% | Available | TRUE | FALSE | Edward's LLC. |  | West Star Bank | [8 empty] | Done | TRUE |  |  |  |  | Samuel Velasco
13388 | Emerald Copper | 1863 | Madeline (GK) | Emerald Park U-5 | 16 | 15 | 27 Trim & Doors | 65% | Available | TRUE | FALSE | Edward's LLC. |  | West Star Bank | [8 empty] | Done | TRUE |  |  |  |  | Samuel Velasco
13389 | Emerald Glass | 1879 | Hailey (GK) | Emerald Park U-5 | 1 | 15 | 26 Tile | 60% | Available | TRUE | FALSE | Edward's LLC. |  | West Star Bank | [8 empty] | Done | TRUE |  |  |  |  | Samuel Velasco
12621 | Fredericksberg | 1856 | Juliana | Garden Park at Mission Ridge U-4 | 6 | 16 | 40 Ready for Walk-Through | 100% | Available | TRUE | FALSE | Edward's LLC. | 2024-02-26 | West Star Bank | [7 empty] | 354950 | C/Beige | TRUE |  |  |  | 2024-07-11 | Ismael Salazar
12629 | Fredericksberg | 1866 | Madeline | Garden Park at Mission Ridge U-4 | 8 | 16 | 40 Ready for Walk-Through | 100% | Available | TRUE | FALSE | Edward's LLC. | 2024-02-23 | West Star Bank | [7 empty] | 354950 | A/Beige | TRUE |  |  |  | 2024-07-11 | Ismael Salazar
12633 | Middlesbrough | 1988 | Savannah | Garden Park at Mission Ridge U-4 | 9 | 17 | 40 Ready for Walk-Through | 100% | Available | TRUE | FALSE | Edward's LLC. | 2024-02-23 | West Star Bank | [7 empty] | 377950 | C/Beige | TRUE |  |  |  | 2024-09-26 | Ismael Salazar
12641 | Middlesbrough | 1856 | Juliana | Garden Park at Mission Ridge U-4 | 11 | 17 | 40 Ready for Walk-Through | 100% | Available | TRUE | FALSE | Edward's LLC. | 2024-02-23 | West Star Bank | [7 empty] | 354950 | A/Beige | TRUE |  |  |  | 2024-10-02 | Ismael Salazar
12645 | Middlesbrough | 1996 | Serenity | Garden Park at Mission Ridge U-4 | 12 | 17 | 40 Ready for Walk-Through | 100% | Available | TRUE | FALSE | Edward's LLC. | 2024-02-23 | West Star Bank | [7 empty] | 379950 | B/Gray | TRUE |  |  |  | 2024-10-08 | Ismael Salazar
12649 | Middlesbrough | 1866 | Madeline | Garden Park at Mission Ridge U-4 | 13 | 17 | 40 Ready for Walk-Through | 100% | Sold | TRUE | TRUE | Edward's LLC. | 2024-02-23 | West Star Bank | Mountain Star Mortage | Conventional | Omar Robles | 2025-10-20 | 2025-12-19 | EH | 915-250-3692 | 354950 | C/Beige | TRUE | Grissel Tovar | Joe Moreno | Priscilla Ramos/Fernanda Cereceres | 2024-10-08 | Ismael Salazar
12656 | Fredericksberg | 1856 | Juliana | Garden Park at Mission Ridge U-4 | 16 | 17 | 40 Ready for Walk-Through | 100% | Available | TRUE | FALSE | Edward's LLC. | 2024-02-26 | West Star Bank | [7 empty] | 354950 | D/Gray | TRUE |  |  |  | 2024-09-17 | Ismael Salazar
12652 | Fredericksberg | 1879 | Hailey | Garden Park at Mission Ridge U-4 | 17 | 17 | 40 Ready for Walk-Through | 100% | Available | TRUE | FALSE | Edward's LLC. | 2024-02-23 | West Star Bank | [7 empty] | 357950 | A/Beige | TRUE |  |  |  | 2024-09-17 | Ismael Salazar
12648 | Fredericksberg | 1825 | Ariana | Garden Park at Mission Ridge U-4 | 18 | 17 | 40 Ready for Walk-Through | 100% | Available | TRUE | FALSE | Edward's LLC. | 2024-02-23 | West Star Bank | [7 empty] | 354950 | B/Gray | TRUE |  |  |  | 2024-09-18 | Ismael Salazar
12644 | Fredericksberg | 1858 | Clarissa | Garden Park at Mission Ridge U-4 | 19 | 17 | 40 Ready for Walk-Through | 100% | Available | TRUE | FALSE | Edward's LLC. | 2024-02-26 | West Star Bank | [7 empty] | 354950 | C/Beige | TRUE |  |  |  | 2024-09-18 | Ismael Salazar
12640 | Fredericksberg | 1866 | Madeline | Garden Park at Mission Ridge U-4 | 20 | 17 | 40 Ready for Walk-Through | 100% | Available | TRUE | FALSE | Edward's LLC. | 2024-02-23 | West Star Bank | [7 empty] | 354950 | D/Gray | TRUE |  |  |  | 2024-09-18 | Ismael Salazar
12636 | Fredericksberg | 1825 | Natalia | Garden Park at Mission Ridge U-4 | 21 | 17 | 40 Ready for Walk-Through | 100% | Sold | TRUE | TRUE | Edward's LLC. | 2024-02-23 | West Star Bank | RMMC | FHA | Eder Corral/Morales | 2025-11-14 | 2025-12-12 | EH | 385-549-4067 | 327950 | A/Beige | TRUE | Lizzet Urbina | Eder Gallardo |  | 2024-10-03 | Ismael Salazar
12632 | Fredericksberg | 1856 | Juliana | Garden Park at Mission Ridge U-4 | 22 | 17 | 40 Ready for Walk-Through | 100% | Available | TRUE | FALSE | Edward's LLC. | 2024-02-26 | West Star Bank | [7 empty] | 354950 | B/Gray | TRUE |  |  |  | 2024-10-03 | Ismael Salazar
12624 | Fredericksberg | 1825 | Ariana | Garden Park at Mission Ridge U-4 | 24 | 17 | 40 Ready for Walk-Through | 100% | Available | TRUE | FALSE | Edward's LLC. | 2024-02-23 | West Star Bank | [7 empty] | 354950 | D/Gray | TRUE |  |  |  | 2024-10-03 | Ismael Salazar
12729 | Fredericksberg | 1866 | Madeline | Garden Park at Mission Ridge U-4 | 8 | 24 | 40 Ready for Walk-Through | 100% | Sold | TRUE | TRUE | Edward's LLC. | 2024-03-12 | Western Heritage | EMI Funding | FHA | Joshua Palomar | 2025-11-25 | 2025-12-23 | EH | 915-202-6529 | 354950 | D/Gray | TRUE | Maria Macias | Peter Huerta | Priscilla Ramos | 2024-07-22 | Samuel Rosales
12733 | Fredericksberg | 1858 | Clarissa | Garden Park at Mission Ridge U-4 | 9 | 24 | 40 Ready for Walk-Through | 100% | Available | TRUE | FALSE | Edward's LLC. | 2024-03-12 | Western Heritage | [7 empty] | 354950 | A/Beige | TRUE |  |  |  | 2024-07-22 | Samuel Rosales
12824 | Middlesbrough | 1825 | Ariana | Garden Park at Mission Ridge U-4 | 7 | 27 | 40 Ready for Walk-Through | 100% | Available | TRUE | FALSE | Edward's LLC. | 2024-07-23 | Western Heritage | [7 empty] | 354950 | Done /Gray | TRUE |  |  |  | 2024-12-05 | Samuel Rosales
12637 | Fredericksberg | 1833 | Ariana (GK) | Garden Park at Mission Ridge U-4 | 10 | 16 | 26 Tile | 60% | Available | TRUE | FALSE | Edward's LLC. | 2025-08-27 | West Star Bank | [7 empty] | 354950 | Done/Beige | TRUE |  |  |  |  | Samuel Rosales
12641 | Fredericksberg | 1879 | Hailey (GK) | Garden Park at Mission Ridge U-4 | 11 | 16 | 26 Tile | 60% | Available | TRUE | FALSE | Edward's LLC. | 2025-08-27 | West Star Bank | [7 empty] | 357950 | Done/Gray | TRUE |  |  |  |  | Samuel Rosales
12645 | Fredericksberg | 1852 | Juliana (GK) | Garden Park at Mission Ridge U-4 | 12 | 16 | 25 Paint | 55% | Available | TRUE | FALSE | Edward's LLC. | 2025-08-27 | West Star Bank | [7 empty] | 354950 | Done/Beige | TRUE |  |  |  |  | Samuel Rosales
12649 | Fredericksberg | 1833 | Natalia (GK) | Garden Park at Mission Ridge U-4 | 13 | 16 | 25 Paint | 55% | Available | TRUE | FALSE | Edward's LLC. | 2025-08-27 | West Star Bank | [7 empty] | 346950 | Done/Greige | TRUE |  |  |  |  | Samuel Rosales
12653 | Fredericksberg | 1863 | Madeline (GK) | Garden Park at Mission Ridge U-4 | 14 | 16 | 25 Paint | 55% | Available | TRUE | FALSE | Edward's LLC. | 2025-08-27 | West Star Bank | [7 empty] | 354950 | Done/Beige | TRUE |  |  |  |  | Samuel Rosales
12657 | Fredericksberg | 1860 | Clarissa (GK) | Garden Park at Mission Ridge U-4 | 15 | 16 | 25 Paint | 55% | Available | TRUE | FALSE | Edward's LLC. | 2025-08-27 | West Star Bank | [7 empty] | 354950 |  | TRUE |  |  |  |  | Samuel Rosales
12661 | Fredericksberg | 1879 | Hailey (GK) | Garden Park at Mission Ridge U-4 | 16 | 16 | 25 Paint | 55% | Available | TRUE | FALSE | Edward's LLC. | 2025-08-27 | West Star Bank | [7 empty] | 360950 |  | TRUE |  |  |  |  | Samuel Rosales
12840 | Fredericksberg | 1863 | Madeline (PT) | Garden Park at Mission Ridge U-4 | 11 | 26 | 38 Building Final / COO | 100% | Sold | TRUE | TRUE | Edward's LLC. | 2025-05-07 | West Star Bank | CMG Home Loans | Conventional | Sandra Gomez | 2025-11-10 | 2025-12-05 | TC | 949-690-3506 | 369950 | Done / Greige | TRUE | Ernesto Medrano | Michelle Medrano | Juan Pablo Amaya | 2025-10-17 | Samuel Rosales
12844 | Fredericksberg | 1860 | Clarissa (PT) | Garden Park at Mission Ridge U-4 | 12 | 26 | 38 Building Final / COO | 100% | Sold | TRUE | TRUE | Edward's LLC. | 2025-05-07 | West Star Bank | Armed Forces Bank | VA | Manuel Palacio/Velez | 2025-11-05 | 2025-12-08 | EH | 631-402-4889 | 369950 | Done / Beige | TRUE | Melanie Aguto | Team Tracy Wilkins/Tracy Wilkins | Arian Wallace | 2025-10-07 | Samuel Rosales
12849 | Middlesbrough | 1833 | Natalia | Garden Park at Mission Ridge U-4 | 15 | 26 | 01 City | 0% | Available | TRUE | FALSE | Edward's LLC. | 2025-05-07 | West Star Bank | [7 empty] | 351950 |  | TRUE |  |  |  |  | Samuel Rosales
12804 | Fredericksberg | 1879 | Hailey (PT) | Garden Park at Mission Ridge U-4 | 2 | 26 | 36 Final Paint | 90% | Available | TRUE | FALSE | Edward's LLC. | 2025-07-16 | West Star Bank | [7 empty] | 369950 | Done/Gray | TRUE |  |  |  |  | Samuel Rosales
12808 | Fredericksberg | 1856 | Juliana (PT) | Garden Park at Mission Ridge U-4 | 3 | 26 | 36 Final Paint | 90% | Available | TRUE | FALSE | Edward's LLC. | 2025-07-16 | West Star Bank | [7 empty] | 369950 | Done/Beige | TRUE |  |  |  |  | Samuel Rosales
12812 | Fredericksberg | 1825 | Natalia (PT) | Garden Park at Mission Ridge U-4 | 4 | 26 | 34 Detail Wall Texture | 85% | Available | TRUE | FALSE | Edward's LLC. | 2025-07-16 | West Star Bank | [7 empty] | 369950 | Done/Gray | TRUE |  |  |  |  | Samuel Rosales
12816 | Fredericksberg | 1866 | Madeline (PT) | Garden Park at Mission Ridge U-4 | 5 | 26 | 38 Building Final / COO | 100% | Sold | TRUE | TRUE | Edward's LLC. | 2025-07-16 | West Star Bank | Cadence Lending Group | Conventional | German Juarez/Zubia | 2025-10-21 | 2025-12-08 | EH | 915-704-1328 | 369950 | Done/Greige | TRUE | Efrain Castaneda | Marcos Bustamante | Priscilla Ramos/Team Edgar Barrio - Vada Garcia | 2025-11-26 | Samuel Rosales
12820 | Fredericksberg | 1858 | Clarissa (PT) | Garden Park at Mission Ridge U-4 | 6 | 26 | 29 Countertops | 70% | Sold | TRUE | TRUE | Edward's LLC. | 2025-07-16 | West Star Bank | RMMC | FHA | Luis Vazquez/Ramirez | 2025-11-26 | 2025-12-29 | EH | 210-323-0218 | 369950 | Done/Gray | TRUE | Pauline Barrio | Erick Flores | Team Edgar Barrio/Alex Morales/Mark Morales |  | Samuel Rosales
12824 | Fredericksberg | 1833 | Ariana (PT) | Garden Park at Mission Ridge U-4 | 7 | 26 | 28 Cabinets | 70% | Available | TRUE | FALSE | Edward's LLC. | 2025-08-05 | West Star Bank | [7 empty] | 369950 | Done/Beige | TRUE |  |  |  |  | Samuel Rosales
12828 | Fredericksberg | 1879 | Hailey (PT) | Garden Park at Mission Ridge U-4 | 8 | 26 | 27 Trim & Doors | 65% | Available | TRUE | FALSE | Edward's LLC. | 2025-08-05 | West Star Bank | [7 empty] | 369950 | Done/Beige | TRUE |  |  |  |  | Samuel Rosales
12832 | Fredericksberg | 1856 | Juliana (PT) | Garden Park at Mission Ridge U-4 | 9 | 26 | 27 Trim & Doors | 65% | Available | TRUE | FALSE | Edward's LLC. | 2025-08-05 | West Star Bank | [7 empty] | 369950 | Done/Gray | TRUE |  |  |  |  | Samuel Rosales
12649 | Hants Circle | 1908 | Hailey (PT) | Garden Park At MR U-4 | 25 | 19 |  |  |  | FALSE | FALSE |  | 2025-11-25 | TRX | [9 empty] | FALSE |  |  |  |  | Samuel Velasco
12653 | Hants Circle | 1894 | Ariana (PT) | Garden Park At MR U-4 | 24 | 19 |  |  |  | FALSE | FALSE |  | 2025-11-25 | TRX | [9 empty] | FALSE |  |  |  |  | Samuel Velasco
12809 | Kingsbury | 1716 | Helsinki | Hillside Park at MR U-5 | 12 | 13 | 38 Building Final / COO | 100% | Available | TRUE | FALSE | Edward's LLC. | 2025-08-07 | West Star Bank | [7 empty] | 324950 | C/Greige | TRUE |  |  |  | 2025-11-11 | Victor Jimenez
12813 | Kingsbury | 1721 | Tokyo | Hillside Park at MR U-5 | 13 | 13 | 38 Building Final / COO | 100% | Available | TRUE | FALSE | Edward's LLC. | 2025-08-07 | West Star Bank | [7 empty] | 324950 | B/Beige | TRUE |  |  |  | 2025-11-11 | Victor Jimenez
12817 | Kingsbury | 1658 | Denver | Hillside Park at MR U-5 | 14 | 13 | 35 Carpet | 90% | Available | TRUE | FALSE | Edward's LLC. | 2025-08-07 | West Star Bank | [7 empty] | 324950 | A/Gray | TRUE |  |  |  |  | Victor Jimenez
12821 | Kingsbury | 1721 | Tokyo | Hillside Park at MR U-5 | 15 | 13 | 35 Carpet | 90% | Available | TRUE | FALSE | Edward's LLC. | 2025-08-07 | West Star Bank | [7 empty] | 324950 | C/Greige | TRUE |  |  |  |  | Victor Jimenez
12825 | Kingsbury | 1716 | Helsinki | Hillside Park at MR U-5 | 16 | 13 | 35 Carpet | 90% | Available | TRUE | FALSE | Edward's LLC. | 2025-08-07 | West Star Bank | [7 empty] | 327950 | B/Beige | TRUE |  |  |  |  | Victor Jimenez
12816 | Kingsbury | 1716 | Helsinki | Hillside Park at MR U-5 | 2 | 42 | 35 Carpet | 90% | Available | TRUE | FALSE | Edward's LLC. | 2025-08-07 | West Star Bank | [7 empty] | 329950 | A/Gray | TRUE |  |  |  |  | Victor Jimenez
12820 | Kingsbury | 1658 | Denver | Hillside Park at MR U-5 | 3 | 42 | 35 Carpet | 90% | Available | TRUE | FALSE | Edward's LLC. | 2025-08-07 | West Star Bank | [7 empty] | 329950 | B/Beige | TRUE |  |  |  |  | Victor Jimenez
900 | Aircoupe | 1879 | Hailey | Hillside Park at MR U-5 | 1 | 40 | 10 Pour Concrete | 20% | Available | FALSE | FALSE | Edward's LLC. | 2025-11-04 | Nusenda Credit Union | [7 empty] | 332950 |  | TRUE |  |  |  |  | Victor Jimenez
904 | Aircoupe | 1721 | Tokyo | Hillside Park at MR U-5 | 2 | 40 | 10 Pour Concrete | 20% | Available | FALSE | FALSE | Edward's LLC. | 2025-11-04 | Nusenda Credit Union | [7 empty] | 329950 |  | TRUE |  |  |  |  | Victor Jimenez
908 | Aircoupe | 1716 | Helsinki | Hillside Park at MR U-5 | 3 | 40 | 10 Pour Concrete | 20% | Available | FALSE | FALSE | Edward's LLC. | 2025-11-04 | Nusenda Credit Union | [7 empty] | 329950 |  | TRUE |  |  |  |  | Victor Jimenez
912 | Aircoupe | 1879 | Hailey | Hillside Park at MR U-5 | 4 | 40 | 11 Frame Walls | 25% | Available | FALSE | FALSE | Edward's LLC. | 2025-11-04 | Nusenda Credit Union | [7 empty] | 329950 |  | TRUE |  |  |  |  | Victor Jimenez
916 | Aircoupe | 1721 | Tokyo | Hillside Park at MR U-5 | 5 | 40 | 11 Frame Walls | 25% | Available | FALSE | FALSE | Edward's LLC. | 2025-11-04 | Nusenda Credit Union | [7 empty] | 332950 |  | TRUE |  |  |  |  | Victor Jimenez
13801 | Centro Vista | 1716 | Helsinki | Horizon Town Center U-4 | 18 | 1 | 18 City Structural Inspection | 40% | Available | TRUE | FALSE | Edward's LLC. | 2025-09-22 | West Star Bank | [7 empty] | 298950 | Done/Beige | TRUE |  |  |  |  | Samuel Velasco
13809 | Centro Vista | 1721 | Tokyo | Horizon Town Center U-4 | 16 | 1 | 26 Tile | 60% | Available | TRUE | FALSE | Edward's LLC. | 2025-09-22 | West Star Bank | [7 empty] | 298950 | Done/Beige | TRUE |  |  |  |  | Samuel Velasco
13813 | Centro Vista | 1658 | Denver | Horizon Town Center U-4 | 15 | 1 | 18 City Structural Inspection | 40% | Available | TRUE | FALSE | Edward's LLC. | 2025-09-22 | West Star Bank | [7 empty] | 298950 | Done/Beige | TRUE |  |  |  |  | Samuel Velasco
13817 | Centro Vista | 1845 | Rio II | Horizon Town Center U-4 | 14 | 1 | 15 Electrical Rough-in | 30% | Available | TRUE | FALSE | Edward's LLC. | 2025-09-22 | West Star Bank | [7 empty] | 298950 | Done/Gray | TRUE |  |  |  |  | Samuel Velasco
13821 | Centro Vista | 1716 | Helsinki | Horizon Town Center U-4 | 13 | 1 | 15 Electrical Rough-in | 30% | Available | TRUE | FALSE | Edward's LLC. | 2025-09-22 | West Star Bank | [7 empty] | 298950 | Done/Gray | TRUE |  |  |  |  | Samuel Velasco
236 | Mar Vista | 1919 | Nailea | Horizon Town Center U-4 | 6 | 1 | 11 Frame Walls | 25% | Available | TRUE | FALSE | Edward's LLC. | 2025-09-22 | West Star Bank | [9 empty] | TRUE |  |  |  |  | Samuel Velasco
252 | Park Vista | 1845 | Rio II | Horizon Town Center U-4 | 27 | 1 | 26 Tile | 60% | Sold | TRUE | FALSE | Edward's LLC. | 2025-09-22 | West Star Bank | Home Plate Mortgage | Conventional | Carlos Amaya | 2025-09-23 | 2026-01-15 | EH | 915-261-2240 | 301950 | Done | TRUE | Gilbert Madrid | Fernando Sanchez | Angel Alba |  | Samuel Velasco
7501 | Clarion Way | 1847 | Rio | Metro Verde Arcadia Ph. 2 | 1 | 0 | 40 Ready for Walk-Through | 100% | Model | TRUE | FALSE | Edward's NM. | 2024-06-10 | Citizens Bank | [7 empty] | 345950 | Done | TRUE |  |  |  | 2024-10-02 | Alfredo Diaz
7509 | Clarion Way | 1658 | Denver | Metro Verde Arcadia Ph. 2 | 2 | 0 | 38 Building Final / COO | 100% | Sold | TRUE | TRUE | Edward's NM. | 2025-06-25 | Citizens Bank | Guild Mortgage | FHA | Jared Singh | 2025-11-06 | 2025-12-04 | EH | 575-571-5149 | 319950 | C/Gray | TRUE | Susie Nelson | Brian Abraham |  | 2025-12-02 | Alfredo Diaz
7517 | Clarion Way | 1716 | Helsinki | Metro Verde Arcadia Ph. 2 | 3 | 0 | 29 Countertops | 70% | Available | TRUE | FALSE | Edward's NM. | 2025-06-25 | Citizens Bank | [7 empty] | 330950 | B/Greige | TRUE |  |  |  |  | Alfredo Diaz
7525 | Clarion Way | 1630 | Berlin | Metro Verde Arcadia Ph. 2 | 4 | 0 | 28 Cabinets | 70% | Available | TRUE | FALSE | Edward's NM. | 2025-06-25 | Citizens Bank | [7 empty] | 319950 | A/Beige | TRUE |  |  |  |  | Alfredo Diaz
7533 | Clarion Way | 1847 | Rio | Metro Verde Arcadia Ph. 2 | 5 | 0 | 28 Cabinets | 70% | Available | TRUE | FALSE | Edward's NM. | 2025-06-25 | Citizens Bank | [7 empty] | 344950 | D/Gray | TRUE |  |  |  |  | Alfredo Diaz
7541 | Clarion Way | 1716 | Helsinki | Metro Verde Arcadia Ph. 2 | 6 | 0 | 28 Cabinets | 70% | Available | TRUE | FALSE | Edward's NM. | 2025-06-25 | Citizens Bank | [7 empty] | 330950 | C/Gray | TRUE |  |  |  |  | Alfredo Diaz
7696 | Alila Way | 1495 | Yoli T | Metro Verde Arcadia Ph. 2 | 25 | 0 | 34 Detail Wall Texture | 85% | Available | TRUE | FALSE | Edward's NM. | 2025-06-25 | Citizens Bank | [7 empty] | 298950 | D/Gray | TRUE |  |  |  |  | Alfredo Diaz
7688 | Alila Way | 1522 | Ayde C | Metro Verde Arcadia Ph. 2 | 26 | 0 | 34 Detail Wall Texture | 85% | Available | TRUE | FALSE | Edward's NM. | 2025-06-25 | Citizens Bank | [7 empty] | 298950 | C/Gray | TRUE |  |  |  |  | Alfredo Diaz
7680 | Alila Way | 1527 | Carmella T | Metro Verde Arcadia Ph. 2 | 27 | 0 | 33 Detail Wall Texture | 80% | Pending | TRUE | FALSE | Edward's NM. | 2025-06-25 | Citizens Bank | [7 empty] | 298950 | D/Gray | TRUE |  |  |  |  | Alfredo Diaz
7672 | Alila Way | 1581 | Karla C | Metro Verde Arcadia Ph. 2 | 28 | 0 | 38 Building Final / COO | 100% | Pending | TRUE | FALSE | Edward's NM. | 2025-06-18 | Citizens Bank | [7 empty] | 298950 | A/Beige | TRUE |  |  |  | 2025-12-02 | Alfredo Diaz
7664 | Alila Way | 1495 | Yoli C | Metro Verde Arcadia Ph. 2 | 29 | 0 | 36 Final Paint | 90% | Available | TRUE | FALSE | Edward's NM. | 2025-06-18 | Citizens Bank | [7 empty] | 298950 | C/Gray | TRUE |  |  |  |  | Alfredo Diaz
7656 | Alila Way | 1522 | Ayde T | Metro Verde Arcadia Ph. 2 | 30 | 0 | 38 Building Final / COO | 100% | Available | TRUE | FALSE | Edward's NM. | 2025-06-18 | Citizens Bank | [7 empty] | 298950 | B/Greige | TRUE |  |  |  | 2025-11-17 | Alfredo Diaz
7648 | Alila Way | 1527 | Carmella C | Metro Verde Arcadia Ph. 2 | 31 | 0 | 38 Building Final / COO | 100% | Sold | TRUE | TRUE | Edward's NM. | 2025-06-18 | Citizens Bank | Guild Mortgage | Conventional | Tyler Ramm | 2025-11-03 | 2025-12-18 | EH | 845-337-0649 | 298950 | C/Gray | TRUE | Susie Nelson | Traci Conner | Brian Abraham | 2025-10-30 | Alfredo Diaz
7632 | Alila Way | 1522 | Ayde C | Metro Verde Arcadia Ph. 2 | 33 | 0 | 38 Building Final / COO | 100% | Sold | TRUE | TRUE | Edward's NM. | 2025-06-11 | Citizens Bank | Price Mortgage | Non-QM | Angelica Diaz | 2025-11-03 | 2025-11-25 | EH | 203-917-6199 | 298950 | A/Beige | TRUE | Marco Milton | Bradford Nordquist Sr. |  | 2025-10-30 | Alfredo Diaz
7624 | Alila Way | 1495 | Yoli T | Metro Verde Arcadia Ph. 2 | 34 | 0 | 38 Building Final / COO | 100% | Sold | TRUE | TRUE | Edward's NM. | 2025-06-11 | Citizens Bank | Nusenda Credit Union | FHA | Martin Venegas/Almanza | 2025-10-15 | 2025-11-14 | EH | 915-888-9072 | 298950 | B/Greige | TRUE | Andrew Vallejo | Patrick Ortega |  | 2025-10-17 | Alfredo Diaz
7600 | Alila Way | 1495 | Yoli C | Metro Verde Arcadia Ph. 2 | 37 | 0 | 38 Building Final / COO | 100% | Available | TRUE | FALSE | Edward's NM. | 2025-06-11 | Citizens Bank | [7 empty] | 301950 | A/Beige | TRUE |  |  |  | 2025-09-16 | Alfredo Diaz
7549 | Clarion Way | 1658 | Denver | Metro Verde Arcadia Ph. 2 | 7 | 0 | 28 Cabinets | 70% | Available | TRUE | FALSE | Edward's NM. | 2025-07-31 | Citizens Bank | [7 empty] | 319950 | A/Beige | TRUE |  |  |  |  | Alfredo Diaz
7557 | Clarion Way | 1716 | Helsinki | Metro Verde Arcadia Ph. 2 | 8 | 0 | 25 Paint | 55% | Available | TRUE | FALSE | Edward's NM. | 2025-07-31 | Citizens Bank | [7 empty] | 330950 | B/Gray | TRUE |  |  |  |  | Alfredo Diaz
7565 | Clarion Way | 1630 | Berlin | Metro Verde Arcadia Ph. 2 | 9 | 0 | 25 Paint | 55% | Available | TRUE | FALSE | Edward's NM. | 2025-07-31 | Citizens Bank | [7 empty] | 319950 | C/Beige | TRUE |  |  |  |  | Alfredo Diaz
7573 | Clarion Way | 1658 | Denver | Metro Verde Arcadia Ph. 2 | 10 | 0 | 26 Tile | 60% | Available | TRUE | FALSE | Edward's NM. | 2025-07-31 | Citizens Bank | [7 empty] | 319950 | D/Greige | TRUE |  |  |  |  | Alfredo Diaz
7581 | Clarion Way | 1716 | Helsinki | Metro Verde Arcadia Ph. 2 | 11 | 0 | 26 Tile | 60% | Available | TRUE | FALSE | Edward's NM. | 2025-07-31 | Citizens Bank | [7 empty] | 330950 | Done | TRUE |  |  |  |  | Alfredo Diaz
7589 | Clarion Way | 1630 | Berlin | Metro Verde Arcadia Ph. 2 | 12 | 0 | 26 Tile | 60% | Available | TRUE | FALSE | Edward's NM. |  | Citizens Bank | [7 empty] | 319950 | A/Beige | TRUE |  |  |  |  | Alfredo Diaz
7597 | Clarion Way | 1879 | Hailey | Metro Verde Arcadia Ph. 2 | 13 | 0 | 28 Cabinets | 70% | Sold | TRUE | TRUE | Edward's NM. | 2025-10-03 | Citizens Bank | Guild Mortgage | FHA | Michael Reyes | 2025-11-25 | 2025-01-28 | EH | 480-572-2204 | 388950 | B/Gray | TRUE | Susie Nelson | Bradford Nordquist Sr. |  |  | Alfredo Diaz
3748 | Daybreak | 1863 | Madeline | Metro Verde Arcadia Ph. 2 | 38 | 0 | 20 Insulation | 40% | Available | TRUE | FALSE | Edward's NM. |  | Citizens Bank | [7 empty] | 377950 | C/Beige | TRUE |  |  |  |  | Alfredo Diaz
3742 | Daybreak | 1852 | Juliana | Metro Verde Arcadia Ph. 2 | 39 | 0 | 20 Insulation | 40% | Available | TRUE | FALSE | Edward's NM. |  | Citizens Bank | [7 empty] | 374950 | D/Greige | TRUE |  |  |  |  | Alfredo Diaz
3736 | Daybreak | 1833 | Ariana | Metro Verde Arcadia Ph. 2 | 40 | 0 | 18 City Structural Inspection | 40% | Available | TRUE | FALSE | Edward's NM. | 2025-08-14 | Citizens Bank | [7 empty] | 374950 | A/Beige | TRUE |  |  |  |  | Alfredo Diaz
3730 | Daybreak | 1879 | Hailey | Metro Verde Arcadia Ph. 2 | 41 | 0 | 21 Sheetrock Install | 45% | Available | TRUE | FALSE | Edward's NM. | 2025-08-14 | Citizens Bank | [7 empty] | 374950 | B/Gray | TRUE |  |  |  |  | Alfredo Diaz
3724 | Daybreak | 1863 | Madeline | Metro Verde Arcadia Ph. 2 | 42 | 0 | 23 Texture | 50% | Available | TRUE | FALSE | Edward's NM. | 2025-08-14 | Citizens Bank | [7 empty] | 374950 | C/Beige | TRUE |  |  |  |  | Alfredo Diaz
3718 | Daybreak | 1852 | Juliana | Metro Verde Arcadia Ph. 2 | 43 | 0 | 21 Sheetrock Install | 45% | Available | TRUE | FALSE | Edward's NM. | 2025-08-14 | Citizens Bank | [7 empty] | 374950 | Done/Beige | TRUE |  |  |  |  | Alfredo Diaz
3712 | Daybreak | 1833 | Ariana | Metro Verde Arcadia Ph. 2 | 44 | 0 | 20 Insulation | 40% | Available | TRUE | FALSE | Edward's NM. | 2025-08-14 | Citizens Bank | [7 empty] | 374950 |  | TRUE |  |  |  |  | Alfredo Diaz
3706 | Daybreak | 1879 | Hailey | Metro Verde Arcadia Ph. 2 | 45 | 0 | 20 Insulation | 40% | Available | TRUE | FALSE | Edward's NM. | 2025-08-21 | Citizens Bank | [7 empty] | 377950 | Done/Gray | TRUE |  |  |  |  | Alfredo Diaz
7935 | San Eduardo | 1658 | Denver | Metro Verde Arcadia Ph. 2 | 91 | 0 | 25 Paint | 55% | Available | TRUE | FALSE | Edward's NM. |  | Citizens Bank | [7 empty] | 329950 | C/Beige | TRUE |  |  |  |  | Alfredo Diaz
7944 | San Eduardo | 1879 | Hailey | Metro Verde Arcadia Ph. 2 | 92 | 0 | 25 Paint | 55% | Available | TRUE | FALSE | Edward's NM. | 2025-08-21 | Citizens Bank | [7 empty] | 388950 | A/Beige | TRUE |  |  |  |  | Alfredo Diaz
7710 | San Eduardo | 1879 | Hailey | Metro Verde Arcadia Ph. 2 | 105 | 0 | 25 Paint | 55% | Available | TRUE | FALSE | Edward's NM. | 2025-08-21 | Citizens Bank | [7 empty] | 388950 | D/Greige | TRUE |  |  |  |  | Alfredo Diaz
2416 | Cardinal | 1503 | Paris | Monte Cielo Ph. 1 | 1 | 0 | 32 Electrical/Plumbing/HVAC Finals | 80% | Available | TRUE | FALSE | Edward's RGV | 2025-04-10 | West Star Bank | [7 empty] | 277950 | Done | TRUE |  |  |  |  | Irving Gallardo
2412 | Cardinal | 1446 | Lisboa | Monte Cielo Ph. 1 | 2 | 0 | 36 Final Paint | 90% | Available | TRUE | FALSE | Edward's RGV |  | West Star Bank | [7 empty] | 277950 |  | TRUE |  |  |  |  | Irving Gallardo
2408 | Cardinal | 1510 | Monaco | Monte Cielo Ph. 1 | 3 | 0 | 32 Electrical/Plumbing/HVAC Finals | 80% | Available | TRUE | FALSE | Edward's RGV | 2025-04-07 | West Star Bank | [7 empty] | 277950 | Done | TRUE |  |  |  |  | Irving Gallardo
2404 | Cardinal | 1503 | Paris | Monte Cielo Ph. 1 | 4 | 0 | 36 Final Paint | 90% | Available | TRUE | FALSE | Edward's RGV |  | West Star Bank | [7 empty] | 277950 |  | TRUE |  |  |  |  | Irving Gallardo
2400 | Cardinal | 1446 | Lisboa | Monte Cielo Ph. 1 | 5 | 0 | 36 Final Paint | 90% | Available | TRUE | FALSE | Edward's RGV |  | West Star Bank | [7 empty] | 277950 |  | TRUE |  |  |  |  | Irving Gallardo
2320 | Cardinal | 1510 | Monaco | Monte Cielo Ph. 1 | 6 | 0 | 36 Final Paint | 90% | Available | TRUE | FALSE | Edward's RGV |  | West Star Bank | [7 empty] | 277950 | Done | TRUE |  |  |  |  | Irving Gallardo
2316 | Cardinal | 1570 | Vienna | Monte Cielo Ph. 1 | 7 | 0 | 32 Electrical/Plumbing/HVAC Finals | 80% | Available | TRUE | FALSE | Edward's RGV |  | West Star Bank | [7 empty] | 277950 | Done | TRUE |  |  |  |  | Irving Gallardo
2312 | Cardinal | 1503 | Paris | Monte Cielo Ph. 1 | 8 | 0 | 36 Final Paint | 90% | Available | TRUE | FALSE | Edward's RGV | 2025-03-04 | West Star Bank | [7 empty] | 277950 | Done | TRUE |  |  |  |  | Irving Gallardo
2308 | Cardinal | 1446 | Lisboa | Monte Cielo Ph. 1 | 9 | 0 | 32 Electrical/Plumbing/HVAC Finals | 80% | Available | TRUE | FALSE | Edward's RGV |  | West Star Bank | [7 empty] | 277950 | Done | TRUE |  |  |  |  | Irving Gallardo
2304 | Cardinal | 1510 | Monaco | Monte Cielo Ph. 1 | 10 | 0 | 25 Paint | 55% | Available | TRUE | FALSE | Edward's RGV |  | West Star Bank | [7 empty] | 277950 |  | TRUE |  |  |  |  | Irving Gallardo
2300 | Cardinal | 1570 | Vienna | Monte Cielo Ph. 1 | 11 | 0 | 25 Paint | 55% | Available | TRUE | FALSE | Edward's RGV |  | West Star Bank | [7 empty] | 277950 |  | TRUE |  |  |  |  | Irving Gallardo
2405 | Cardinal | 1570 | Vienna | Monte Cielo Ph. 1 | 13 | 0 | 29 Countertops | 70% | Available | TRUE | FALSE | Edward's RGV |  | West Star Bank | [7 empty] | 279950 |  | TRUE |  |  |  |  | Irving Gallardo
2404 | Zinnia | 1446 | Lisboa | Monte Cielo Ph. 1 | 60 | 0 | 38 Building Final / COO | 100% | Available | TRUE | FALSE | Edward's RGV | 2025-03-04 | West Star Bank | [7 empty] | 279950 | Done | TRUE |  |  |  |  | Irving Gallardo
2401 | Zinnia | 1503 | Paris | Monte Cielo Ph. 1 | 62 | 0 | 36 Final Paint | 90% | Available | TRUE | FALSE | Edward's RGV |  | West Star Bank | [7 empty] | 279950 |  | TRUE |  |  |  |  | Irving Gallardo
2400 | Blue Sky | 1510 | Monaco | Monte Cielo Ph. 1 | 107 | 0 | 21 Sheetrock Install | 45% | Available | TRUE | FALSE | Edward's RGV |  | West Star Bank | [7 empty] | 279950 |  | TRUE |  |  |  |  | Irving Gallardo
3505 | Kerps | 1510 | Monaco | Monte Cielo Ph. 1 | 109 | 0 | 29 Countertops | 70% | Available | TRUE | FALSE | Edward's RGV | 2025-04-07 | West Star Bank | [7 empty] | 282950 |  | TRUE |  |  |  |  | Irving Gallardo
3501 | Kerps | 1503 | Paris | Monte Cielo Ph. 1 | 110 | 0 | 32 Electrical/Plumbing/HVAC Finals | 80% | Available | TRUE | FALSE | Edward's RGV | 2025-04-02 | West Star Bank | [7 empty] | 282950 |  | TRUE |  |  |  |  | Irving Gallardo
3417 | Kerps | 1446 | Lisboa | Monte Cielo Ph. 1 | 111 | 0 | 38 Building Final / COO | 100% | Available | TRUE | FALSE | Edward's RGV | 2025-03-04 | West Star Bank | [7 empty] | 282950 | Done | TRUE |  |  |  |  | Irving Gallardo
3413 | Kerps | 1570 | Vienna | Monte Cielo Ph. 1 | 112 | 0 | 38 Building Final / COO | 100% | Available | TRUE | FALSE | Edward's RGV |  | West Star Bank | [7 empty] | 282950 |  | TRUE |  |  |  |  | Irving Gallardo
3401 | Kerps | 1446 | Lisboa | Monte Cielo Ph. 1 | 115 | 0 | 37 Foreman Checklist Approval | 90% | Available | TRUE | FALSE | Edward's RGV | 2025-03-04 | TRX | [7 empty] | 282950 |  | TRUE |  |  |  |  | Irving Gallardo
3405 | Kerps | 1503 | Paris | Monte Cielo Ph. 1 | 114 | 0 | 38 Building Final / COO | 100% | Sold | TRUE | TRUE | Edward's RGV | 2025-03-26 | TRX | Cross Country Mortgage | FHA | Eric Sandoval | 2025-11-04 | 2025-12-01 | EH | 956-975-0666 | 282950 |  | TRUE | Nate Lambert | Jose Arellano | Athena Vasquez | 2025-04-02 | Irving Gallardo
2417 | Blue Sky | 1503 | Paris | Monte Cielo Ph. 1 | 118 | 0 | 38 Building Final / COO | 100% | Available | TRUE | FALSE | Edward's RGV | 2025-04-02 | TRX | [7 empty] | 279950 | RGV WHITE | TRUE |  |  |  | 2025-07-11 | Irving Gallardo
2421 | Blue Sky | 1510 | Monaco | Monte Cielo Ph. 1 | 117 | 0 | 38 Building Final / COO | 100% | Available | TRUE | FALSE | Edward's RGV | 2025-04-07 | TRX | [7 empty] | 279950 | RGV TAN | TRUE |  |  |  | 2025-07-11 | Irving Gallardo
3409 | Kerps | 1510 | Monaco | Monte Cielo Ph. 1 | 113 | 0 | 38 Building Final / COO | 100% | Sold | TRUE | TRUE | Edward's RGV | 2025-04-07 | TRX | Wall Street Wholesale Lender, LLC. | Conventional | Shital Agarwal | 2025-11-18 | 2025-12-11 | TC | 956-279-2247 | 282950 |  | TRUE | Ashish Bhusare | Marc Moran | Lauren Roel | 2025-04-08 | Irving Gallardo
933 | Sandhurst | 1438 | Yoli F | Painted Desert at Mission Ridge U-4 | 11 | 17 | 40 Ready for Walk-Through | 100% | Pending | TRUE | FALSE | Edward's LLC. | 2024-09-20 | West Star Bank | [7 empty] | 274950 | C/Gray | TRUE |  |  |  | 2024-12-05 | Ismael Salazar
13733 | Lorenz | 1495 | Yoli T | Painted Desert at Mission Ridge U-4 | 4 | 2 | 40 Ready for Walk-Through | 100% | Available | TRUE | FALSE | Edward's LLC. | 2024-12-31 | West Star Bank | [7 empty] | 279950 | C/Gray | TRUE |  |  |  | 2025-03-18 | Ismael Salazar
13741 | Lorenz | 1522 | Ayde T | Painted Desert at Mission Ridge U-4 | 6 | 2 | 40 Ready for Walk-Through | 100% | Available | TRUE | FALSE | Edward's LLC. | 2024-12-31 | West Star Bank | [7 empty] | 279950 | E/Beige | TRUE |  |  |  | 2025-03-31 | Ismael Salazar
13745 | Lorenz | 1495 | Yoli T | Painted Desert at Mission Ridge U-4 | 7 | 2 | 40 Ready for Walk-Through | 100% | Available | TRUE | FALSE | Edward's LLC. | 2024-12-31 | West Star Bank | [7 empty] | 279950 | A/Beige | TRUE |  |  |  | 2025-03-31 | Ismael Salazar
13785 | Lorenz | 1495 | Yoli C | Painted Desert at Mission Ridge U-4 | 3 | 4 | 40 Ready for Walk-Through | 100% | Available | TRUE | FALSE | Edward's LLC. | 2024-12-31 | West Star Bank | [7 empty] | 279950 | E/Beige | TRUE |  |  |  | 2025-04-14 | Ismael Salazar
13973 | Lorenz | 1527 | Carmella T | Painted Desert at Mission Ridge U-4 | 4 | 6 | 40 Ready for Walk-Through | 100% | Sold | TRUE | TRUE | Edward's LLC. | 2025-01-10 | West Star Bank | Cardinal Financial Company | VA | Rockwell Botchway | 2025-11-14 | 2025-12-12 | EH | 915-799-6342 | 279950 | E/Beige | TRUE | Diana Navarro | Edgar Navarro | Audrey Gutierrez | 2025-05-06 | Ismael Salazar
13769 | Loreina Luz | 1522 | Ayde C | Painted Desert at Mission Ridge U-4 | 21 | 9 | 40 Ready for Walk-Through | 100% | Model | TRUE | FALSE | Edward's LLC. | 2025-03-26 | West Star Bank | [7 empty] | 282950 | A/ Beige | TRUE |  |  |  | 2025-06-02 | Ismael Salazar
13741 | Loreina Luz | 1527 | Carmella C | Painted Desert at Mission Ridge U-4 | 28 | 9 | 40 Ready for Walk-Through | 100% | Sold | TRUE | TRUE | Edward's LLC. | 2025-03-31 | West Star Bank | Change Home Mortgage | FHA | Jesus Gandara/Alvidrez | 2025-09-24 | 2025-11-17 | EH | 915-996-3145 | 279950 | A/Beige | TRUE | Brian Martinez | Ronald Nunez-Rupert | Juan Pablo Amaya | 2025-06-13 | Ismael Salazar
13436 | Cinderford | 1650 | Jazmine F | Painted Sky at Mission Ridge U-3 | 20 | 20 | 40 Ready for Walk-Through | 100% | Available | TRUE | FALSE | Edward's LLC. | 2024-01-12 01:00 | West Star Bank | [7 empty] | 309950 | C/Gray | TRUE |  |  |  | 2024-06-20 | Ismael Salazar
818 | Harpendem | 1700 | Danielle F | Painted Sky at Mission Ridge U-3 | 13 | 19 | 40 Ready for Walk-Through | 100% | Available | TRUE | FALSE | Edward's LLC. | 2025-02-05 | TRX | [7 empty] | 349950 | Done / Beige | TRUE |  |  |  | 2025-05-28 | Ismael Salazar
858 | Harpendem | 1833 | Ariana (PT) | Painted Sky at Mission Ridge U-3 | 5 | 13 | 23 Texture | 50% | Available | TRUE | FALSE | Edward's LLC. | 2025-09-02 | West Star Bank | [8 empty] | Done/Gray | TRUE |  |  |  |  | Samuel Rosales
854 | Harpendem | 1879 | Hailey (PT) | Painted Sky at Mission Ridge U-3 | 4 | 13 | 25 Paint | 55% | Available | TRUE | FALSE | Edward's LLC. | 2025-09-02 | West Star Bank | [8 empty] | Done/Beige | TRUE |  |  |  |  | Samuel Rosales
850 | Harpendem | 1721 | Tokyo (PT) | Painted Sky at Mission Ridge U-3 | 3 | 13 | 25 Paint | 55% | Available | TRUE | FALSE | Edward's LLC. | 2025-09-02 | West Star Bank | [8 empty] | Done/Gray | TRUE |  |  |  |  | Samuel Rosales
813 | Paseo Pacifico | 1504 | Ayde II F | Paseo Del Este U-9 Phase 1 | 14 | 51 | 40 Ready for Walk-Through | 100% | Available | TRUE | FALSE | Edward's LLC. | 2024-05-15 | West Star Bank | [7 empty] | 279950 | A/Beige | TRUE |  |  |  | 2024-10-03 | Samuel Rosales
833 | Paseo Pacifico | 1490 | Carmella II F | Paseo Del Este U-9 Phase 1 | 19 | 51 | 40 Ready for Walk-Through | 100% | Available | TRUE | FALSE | Edward's LLC. | 2024-05-15 | West Star Bank | [7 empty] | 279950 | B/Gray | TRUE |  |  |  | 2025-01-07 | Samuel Rosales
837 | Paseo Pacifico | 1438 | Yoli F | Paseo Del Este U-9 Phase 1 | 20 | 51 | 40 Ready for Walk-Through | 100% | Available | TRUE | FALSE | Edward's LLC. | 2024-05-15 | West Star Bank | [7 empty] | 279950 | C/Gray | TRUE |  |  |  | 2025-01-07 | Samuel Rosales
13921 | Paseo Bosque | 1438 | Yoli F | Paseo Del Este U-9 Phase 1 | 8 | 55 | 40 Ready for Walk-Through | 100% | Available | TRUE | FALSE | Edward's LLC. | 2024-05-15 | West Star Bank | [7 empty] | 279950 | B/Gray | TRUE |  |  |  | 2024-10-16 | Samuel Rosales
841 | Paseo Tranquilo | 1489 | Karla IV F | Paseo Del Este U-9 Phase 1 | 13 | 56 | 40 Ready for Walk-Through | 100% | Available | TRUE | FALSE | Edward's LLC. | 2024-05-15 | West Star Bank | [7 empty] | 274950 | B/Gray | TRUE |  |  |  | 2024-12-03 | Samuel Rosales
837 | Paseo Tranquilo | 1438 | Yoli F | Paseo Del Este U-9 Phase 1 | 14 | 55 | 37 Foreman Checklist Approval | 90% | Available | TRUE | FALSE | Edward's LLC. | 2024-05-15 | West Star Bank | [7 empty] | 279950 | C/Gray | TRUE |  |  |  | 2024-12-03 | Samuel Rosales
828 | Paseo Pacifico | 1438 | Yoli F | Paseo Del Este U-9 Phase 1 | 5 | 56 | 40 Ready for Walk-Through | 100% | Available | TRUE | FALSE | Edward's LLC. | 2024-11-07 | West Star Bank | [7 empty] | 279950 | B/Beige | TRUE |  |  |  | 2025-02-18 | Samuel Rosales
824 | Paseo Pacifico | 1490 | Carmella II F | Paseo Del Este U-9 Phase 1 | 6 | 56 | 40 Ready for Walk-Through | 100% | Available | TRUE | FALSE | Edward's LLC. | 2024-11-07 | West Star Bank | [7 empty] | 279950 | C/Gray | TRUE |  |  |  | 2025-05-07 | Samuel Rosales
833 | Paseo Tranquilo | 1490 | Carmella II F | Paseo Del Este U-9 Phase 1 | 15 | 56 | 37 Foreman Checklist Approval | 90% | Available | TRUE | FALSE | Edward's LLC. | 2024-11-07 | West Star Bank | [7 empty] | 279950 | A/Beige | TRUE |  |  |  | 2025-04-04 | Samuel Rosales
829 | Paseo Tranquilo | 1504 | Ayde II F | Paseo Del Este U-9 Phase 1 | 16 | 56 | 37 Foreman Checklist Approval | 90% | Available | TRUE | FALSE | Edward's LLC. | 2024-11-07 | West Star Bank | [7 empty] | 279950 | E/Beige | TRUE |  |  |  | 2025-04-04 | Samuel Rosales
820 | Paseo Pacifico | 1518 | Ayde M | Paseo Del Este U-9 Phase 1 | 7 | 56 | 40 Ready for Walk-Through | 100% | Available | TRUE | FALSE | Edward's LLC. | 2024-11-19 | West Star Bank | [7 empty] | 279950 | D/Gray | TRUE |  |  |  |  | Samuel Rosales
808 | Paseo Pacifico | 1490 | Carmella II F | Paseo Del Este U-9 Phase 1 | 10 | 56 | 37 Foreman Checklist Approval | 90% | Available | TRUE | FALSE | Edward's LLC. | 2024-11-19 | West Star Bank | [7 empty] | 279950 | B/Greige | TRUE |  |  |  |  | Samuel Rosales
821 | Paseo Tranquilo | 1438 | Yoli F | Paseo Del Este U-9 Phase 1 | 18 | 56 | 37 Foreman Checklist Approval | 90% | Available | TRUE | FALSE | Edward's LLC. | 2024-12-10 | West Star Bank | [7 empty] | 279950 | B/Greige | TRUE |  |  |  | 2025-05-07 | Samuel Rosales
809 | Paseo Tranquilo | 1438 | Yoli F | Paseo Del Este U-9 Phase 1 | 21 | 56 | 37 Foreman Checklist Approval | 90% | Available | TRUE | FALSE | Edward's LLC. | 2024-12-10 | West Star Bank | [7 empty] | 279950 | E/Beige | TRUE |  |  |  |  | Samuel Rosales
13908 | Paseo Perlas | 1532 | Arely T | Paseo Del Este U-9 Phase 1 | 11 | 46 | 29 Countertops | 70% | Available | TRUE | FALSE | Edward's LLC. | 2025-09-16 | West Star Bank | [7 empty] | 279950 | A/Beige | TRUE |  |  |  |  | Victor Jimenez
13909 | Paseo Perlas | 1527 | Carmella T | Paseo Del Este U-9 Phase 1 | 12 | 51 | 29 Countertops | 70% | Available | TRUE | FALSE | Edward's LLC. | 2025-09-16 | West Star Bank | [7 empty] | 282950 | B/Beige | TRUE |  |  |  |  | Victor Jimenez
13912 | Paseo Perlas | 1583 | Karla T | Paseo Del Este U-9 Phase 1 | 12 | 46 | 28 Cabinets | 70% | Available | TRUE | FALSE | Edward's LLC. | 2025-09-16 | West Star Bank | [7 empty] | 279950 | C/Gray | TRUE |  |  |  |  | Victor Jimenez
13916 | Paseo Perlas | 1527 | Carmella T | Paseo Del Este U-9 Phase 1 | 13 | 46 | 26 Tile | 60% | Available | TRUE | FALSE | Edward's LLC. | 2025-09-16 | West Star Bank | [7 empty] | 279950 | D/Beige | TRUE |  |  |  |  | Victor Jimenez
13920 | Paseo Perlas | 1522 | Ayde T | Paseo Del Este U-9 Phase 1 | 14 | 46 | 26 Tile | 60% | Available | TRUE | FALSE | Edward's LLC. | 2025-09-16 | West Star Bank | [7 empty] | 279950 | E/Gray | TRUE |  |  |  |  | Victor Jimenez
13924 | Paseo Perlas | 1583 | Karla T | Paseo Del Este U-9 Phase 1 | 15 | 46 | 14 HVAC & Plumbing Rough-in | 30% | Available | TRUE | FALSE | Edward's LLC. | 2025-10-06 | West Star Bank | [7 empty] | 279950 | A/Beige | TRUE |  |  |  |  | Victor Jimenez
13928 | Paseo Perlas | 1527 | Carmella T | Paseo Del Este U-9 Phase 1 | 16 | 46 | 14 HVAC & Plumbing Rough-in | 30% | Available | TRUE | FALSE | Edward's LLC. | 2025-10-06 | West Star Bank | [7 empty] | 279950 | C/Gray | TRUE |  |  |  |  | Victor Jimenez
13932 | Paseo Perlas | 1532 | Arely T | Paseo Del Este U-9 Phase 1 | 17 | 46 | 14 HVAC & Plumbing Rough-in | 30% | Available | TRUE | FALSE | Edward's LLC. | 2025-10-06 | West Star Bank | [7 empty] | 279950 | E/Gray | TRUE |  |  |  |  | Victor Jimenez
13936 | Paseo Perlas | 1522 | Ayde T | Paseo Del Este U-9 Phase 1 | 18 | 46 | 14 HVAC & Plumbing Rough-in | 30% | Available | TRUE | FALSE | Edward's LLC. | 2025-10-06 | West Star Bank | [7 empty] | 282950 | B/Beige | TRUE |  |  |  |  | Victor Jimenez
13945 | Paseo Alegre | 1532 | Arely T | Paseo del Este U-9 Phase 3 | 15 | 75 | 11 Frame Walls | 25% | Available | TRUE | FALSE | Edward's LLC. | 2025-11-04 | West Star Bank | [9 empty] | TRUE |  |  |  |  | Victor Jimenez
13949 | Paseo Alegre | 1527 | Carmella T | Paseo del Este U-9 Phase 3 | 16 | 75 | 11 Frame Walls | 25% | Available | TRUE | FALSE | Edward's LLC. | 2025-11-04 | West Star Bank | [9 empty] | TRUE |  |  |  |  | Victor Jimenez
13953 | Paseo Alegre | 1581 | Karla C | Paseo del Este U-9 Phase 3 | 17 | 75 | 10 Pour Concrete | 20% | Available | TRUE | FALSE | Edward's LLC. | 2025-11-04 | West Star Bank | [9 empty] | TRUE |  |  |  |  | Victor Jimenez
13957 | Paseo Alegre | 1522 | Ayde T | Paseo del Este U-9 Phase 3 | 18 | 75 | 10 Pour Concrete | 20% | Available | TRUE | FALSE | Edward's LLC. | 2025-11-04 | [10 empty] | TRUE |  |  |  |  | Victor Jimenez
13961 | Paseo Alegre | 1583 | Karla T | Paseo del Este U-9 Phase 3 | 19 | 75 | 10 Pour Concrete | 20% | Available | TRUE | FALSE | Edward's LLC. | 2025-11-04 | West Star Bank | [9 empty] | TRUE |  |  |  |  | Victor Jimenez
13965 | Paseo Alegre | 1522 | Ayde C | Paseo del Este U-9 Phase 3 | 20 | 75 | 10 Pour Concrete | 20% | Available | TRUE | FALSE | Edward's LLC. | 2025-11-04 | West Star Bank | [9 empty] | TRUE |  |  |  |  | Victor Jimenez
13932 | Paseo Alegre | 1522 | Ayde C | Paseo del Este U-9 Phase 3 | 9 | 79 |  |  | Available | TRUE | FALSE | Edward's LLC. |  | West Star Bank | [9 empty] | FALSE
13936 | Paseo Alegre | 1583 | Karla T | Paseo del Este U-9 Phase 3 | 10 | 79 |  |  | Available | TRUE | FALSE | Edward's LLC. |  | West Star Bank | [9 empty] | FALSE
13940 | Paseo Alegre | 1527 | Carmella T | Paseo del Este U-9 Phase 3 | 11 | 79 |  |  | Available | TRUE | FALSE | Edward's LLC. |  | West Star Bank | [9 empty] | FALSE
13944 | Paseo Alegre | 1532 | Arely C | Paseo del Este U-9 Phase 3 | 12 | 79 |  |  | Available | TRUE | FALSE | Edward's LLC. |  | West Star Bank | [9 empty] | FALSE
13948 | Paseo Alegre | 1522 | Ayde T | Paseo del Este U-9 Phase 3 | 13 | 79 |  |  | Available | TRUE | FALSE | Edward's LLC. |  | West Star Bank | [9 empty] | FALSE
13952 | Paseo Alegre | 1583 | Karla T | Paseo del Este U-9 Phase 3 | 14 | 79 |  |  | Available | TRUE | FALSE | Edward's LLC. |  | West Star Bank | [9 empty] | FALSE
13956 | Paseo Alegre | 1522 | Ayde C | Paseo del Este U-9 Phase 3 | 15 | 79 |  |  | Available | TRUE | FALSE | Edward's LLC. |  | West Star Bank | [9 empty] | FALSE
13960 | Paseo Alegre | 1532 | Arely T | Paseo del Este U-9 Phase 3 | 16 | 79 |  |  | Available | TRUE | FALSE | Edward's LLC. |  | West Star Bank | [9 empty] | FALSE
13964 | Paseo Alegre | 1527 | Carmella T | Paseo del Este U-9 Phase 3 | 17 | 79 |  |  | Available | TRUE | FALSE | Edward's LLC. |  | West Star Bank | [9 empty] | FALSE
13968 | Paseo Alegre | 1581 | Karla C | Paseo del Este U-9 Phase 3 | 18 | 79 |  |  | Available | TRUE | FALSE | Edward's LLC. |  | West Star Bank | [9 empty] | FALSE
13972 | Paseo Alegre | 1522 | Ayde T | Paseo del Este U-9 Phase 3 | 19 | 79 |  |  | Available | TRUE | FALSE | Edward's LLC. |  | West Star Bank | [9 empty] | FALSE
101 | Monticello St | 1879 | Hailey (PT) | Rancho Santa Teresa U-2 | 11 | 22 |  |  |  | FALSE | FALSE |  | 2025-09-15 | Citizens Bank | [9 empty] | FALSE
103 | Monticello St | 1863 | Madeline (PT) | Rancho Santa Teresa U-2 | 10 | 22 |  |  |  | FALSE | FALSE |  | 2025-09-15 | Citizens Bank | [9 empty] | FALSE
105 | Monticello St | 1860 | Clarissa (PT) | Rancho Santa Teresa U-2 | 9 | 22 |  |  |  | FALSE | FALSE |  | 2025-09-15 | Citizens Bank | [9 empty] | FALSE
107 | Monticello St | 1833 | Ariana (PT) | Rancho Santa Teresa U-2 | 8 | 22 |  |  |  | FALSE | FALSE |  | 2025-09-15 | Citizens Bank | [9 empty] | FALSE
109 | Monticello St | 1852 | Juliana (PT) | Rancho Santa Teresa U-2 | 7 | 22 |  |  |  | FALSE | FALSE |  | 2025-09-15 | Citizens Bank | [9 empty] | FALSE
2313 | N. Gaytan | 1510 | Monaco | Silverstone Heights | 8 | 0 | 25 Paint | 55% | Available | TRUE | FALSE | Edward's RGV |  | West Star Bank | [9 empty] | TRUE |  |  |  |  | Irving Gallardo
2309 | N. Gaytan | 1570 | Vienna | Silverstone Heights | 9 | 0 | 13 Frame Sheeting | 25% | Available | TRUE | FALSE | Edward's RGV |  | West Star Bank | [9 empty] | TRUE |  |  |  |  | Irving Gallardo
2305 | N. Gaytan | 1503 | Paris | Silverstone Heights | 10 | 0 | 32 Electrical/Plumbing/HVAC Finals | 80% | Available | TRUE | FALSE | Edward's RGV |  | West Star Bank | [9 empty] | TRUE |  |  |  |  | Irving Gallardo
2301 | N. Gaytan | 1446 | Lisboa | Silverstone Heights | 11 | 0 | 32 Electrical/Plumbing/HVAC Finals | 80% | Available | TRUE | FALSE | Edward's RGV |  | West Star Bank | [9 empty] | TRUE |  |  |  |  | Irving Gallardo
2217 | N. Gaytan | 1510 | Monaco | Silverstone Heights | 12 | 0 | 32 Electrical/Plumbing/HVAC Finals | 80% | Available | TRUE | FALSE | Edward's RGV |  | West Star Bank | [9 empty] | TRUE |  |  |  |  | Irving Gallardo
3217 | E. La Cienega | 1510 | Monaco | Silverstone Heights | 99 | 0 | 10 Pour Concrete | 20% | Available | TRUE | FALSE | Edward's RGV |  | West Star Bank | [9 empty] | TRUE |  |  |  |  | Irving Gallardo
13832 | Margaret Ponce | 1522 | Ayde C | Summer Sky North U-1 Ph. 1 | 12 | 2 | 40 Ready for Walk-Through | 100% | Available | TRUE | FALSE | Edward's LLC. | 2025-04-02 | West Star Bank | [7 empty] | 279950 | B/Greige | TRUE |  |  |  | 2025-06-13 | Victor Jimenez
13820 | Margaret Ponce | 1522 | Ayde C | Summer Sky North U-1 Ph. 1 | 15 | 2 | 40 Ready for Walk-Through | 100% | Available | TRUE | FALSE | Edward's LLC. | 2025-04-02 | West Star Bank | [7 empty] | 279950 | A/Beige | TRUE |  |  |  |  | Victor Jimenez
13816 | Margaret Ponce | 1495 | Yoli C | Summer Sky North U-1 Ph. 1 | 16 | 2 | 40 Ready for Walk-Through | 100% | Available | TRUE | FALSE | Edward's LLC. | 2025-04-14 | West Star Bank | [7 empty] | 279950 | B/Greige | TRUE |  |  |  | 2025-07-18 | Victor Jimenez
13812 | Margaret Ponce | 1527 | Carmella C | Summer Sky North U-1 Ph. 1 | 17 | 2 | 40 Ready for Walk-Through | 100% | Sold | TRUE | TRUE | Edward's LLC. | 2025-04-14 | West Star Bank | RMMC | VA | Habarugira Janvier | 2025-11-14 | 2025-12-19 | EH | 346-357-8525 | 279950 | C/Gray | TRUE | Pauline Barrio | Team Jacqueline Rodriguez/Christian Estrada | Diana Romero/Alex Morales | 2025-07-18 | Victor Jimenez
13829 | Margaret Ponce | 1522 | Ayde T | Summer Sky North U-1 Ph. 1 | 21 | 34 | 40 Ready for Walk-Through | 100% | Sold | TRUE | TRUE | Edward's LLC. | 2025-04-14 | West Star Bank | RMMC | VA | Shedrick Battle Jr. | 2025-12-01 | 2025-12-22 | EH | 915-202-1624 | 279950 | A/Beige | TRUE | Ruth Guevara | Germain Ramia | Diana Caballero | 2025-07-23 | Victor Jimenez
13825 | Margaret Ponce | 1495 | Yoli T | Summer Sky North U-1 Ph. 1 | 22 | 34 | 40 Ready for Walk-Through | 100% | Available | TRUE | FALSE | Edward's LLC. | 2025-04-14 | West Star Bank | [7 empty] | 279950 | B/Greige | TRUE |  |  |  | 2025-08-12 | Victor Jimenez
13817 | Margaret Ponce | 1522 | Ayde T | Summer Sky North U-1 Ph. 1 | 24 | 34 | 40 Ready for Walk-Through | 100% | Available | TRUE | FALSE | Edward's LLC. | 2025-04-17 | West Star Bank | [7 empty] | 279950 | D/Beige | TRUE |  |  |  | 2025-08-12 | Victor Jimenez
13809 | Margaret Ponce | 1495 | Yoli T | Summer Sky North U-1 Ph. 1 | 26 | 34 | 40 Ready for Walk-Through | 100% | Available | TRUE | FALSE | Edward's LLC. | 2025-04-17 | West Star Bank | [7 empty] | 279950 | C/Gray | TRUE |  |  |  | 2025-07-29 | Victor Jimenez
13805 | Margaret Ponce | 1527 | Carmella T | Summer Sky North U-1 Ph. 1 | 27 | 34 | 40 Ready for Walk-Through | 100% | Available | TRUE | FALSE | Edward's LLC. | 2025-04-17 | West Star Bank | [7 empty] | 279950 | B/Greige | TRUE |  |  |  | 2025-07-29 | Victor Jimenez
1228 | Indigo Sky | 1522 | Ayde T | Summer Sky North U-1 Ph. 1 | 29 | 34 | 26 Tile | 60% | Available | TRUE | FALSE | Edward's LLC. | 2025-09-09 | West Star Bank | [7 empty] | 279950 | B/Greige | TRUE |  |  |  |  | Victor Jimenez
1252 | Indigo Sky | 1527 | Carmella T | Summer Sky North U-1 Ph. 1 | 35 | 34 | 26 Tile | 60% | Available | TRUE | FALSE | Edward's LLC. | 2025-09-09 | West Star Bank | [7 empty] | 279950 | D/Beige | TRUE |  |  |  |  | Victor Jimenez
13804 | Madero | 1522 | Ayde C | Summer Sky North U-1 Ph. 1 | 2 | 34 | 28 Cabinets | 70% | Available | TRUE | FALSE | Edward's LLC. | 2025-09-09 | West Star Bank | [7 empty] | 279950 | A/Beige | TRUE |  |  |  |  | Victor Jimenez
13808 | Madero | 1527 | Carmella T | Summer Sky North U-1 Ph. 1 | 3 | 34 | 28 Cabinets | 70% | Available | TRUE | FALSE | Edward's LLC. | 2025-09-09 | West Star Bank | [7 empty] | 279950 | B/Greige | TRUE |  |  |  |  | Victor Jimenez
13812 | Madero | 1532 | Arely T | Summer Sky North U-1 Ph. 1 | 4 | 34 | 25 Paint | 55% | Available | TRUE | FALSE | Edward's LLC. | 2025-09-25 | West Star Bank | [7 empty] | 279950 | C/Gray | TRUE |  |  |  |  | Victor Jimenez
13816 | Madero | 1581 | Karla C | Summer Sky North U-1 Ph. 1 | 5 | 34 | 25 Paint | 55% | Available | TRUE | FALSE | Edward's LLC. | 2025-09-09 | West Star Bank | [7 empty] | 279950 | D/Beige | TRUE |  |  |  |  | Victor Jimenez
13837 | Margaret Ponce | 1527 | Carmella T | Summer Sky North U-1 Ph. 1 | 19 | 34 | 25 Paint | 55% | Available | TRUE | FALSE | Edward's LLC. | 2025-09-25 | West Star Bank | [7 empty] | 279950 | A/Beige | TRUE |  |  |  |  | Victor Jimenez
13848 | Margaret Ponce | 1527 | Carmella T | Summer Sky North U-1 Ph. 1 | 17 | 3 | 21 Sheetrock Install | 45% | Available | TRUE | FALSE | Edward's LLC. | 2025-09-25 | West Star Bank | [7 empty] | 279950 | D/Beige | TRUE |  |  |  |  | Victor Jimenez
13852 | Margaret Ponce | 1532 | Arely T | Summer Sky North U-1 Ph. 1 | 16 | 3 | 21 Sheetrock Install | 45% | Available | TRUE | FALSE | Edward's LLC. | 2025-09-25 | West Star Bank | [7 empty] | 279950 | C/Gray | TRUE |  |  |  |  | Victor Jimenez
13856 | Margaret Ponce | 1583 | Karla T | Summer Sky North U-1 Ph. 1 | 15 | 3 | 21 Sheetrock Install | 45% | Available | TRUE | FALSE | Edward's LLC. | 2025-09-25 | West Star Bank | [7 empty] | 279950 | B/Greige | TRUE |  |  |  |  | Victor Jimenez
13860 | Margaret Ponce | 1522 | Ayde T | Summer Sky North U-1 Ph. 1 | 14 | 3 | 14 HVAC & Plumbing Rough-in | 30% | Available | TRUE | FALSE | Edward's LLC. | 2025-10-16 | West Star Bank | [7 empty] | 279950 | C/Gray | TRUE |  |  |  |  | Victor Jimenez
13864 | Margaret Ponce | 1527 | Carmella T | Summer Sky North U-1 Ph. 1 | 13 | 3 | 14 HVAC & Plumbing Rough-in | 30% | Available | TRUE | FALSE | Edward's LLC. | 2025-10-16 | West Star Bank | [7 empty] | 279950 | B/Greige | TRUE |  |  |  |  | Victor Jimenez
13868 | Margaret Ponce | 1532 | Arely T | Summer Sky North U-1 Ph. 1 | 12 | 3 | 14 HVAC & Plumbing Rough-in | 30% | Available | TRUE | FALSE | Edward's LLC. | 2025-10-16 | West Star Bank | [7 empty] | 279950 | A/Beige | TRUE |  |  |  |  | Victor Jimenez
13872 | Margaret Ponce | 1583 | Karla T | Summer Sky North U-1 Ph. 1 | 11 | 3 | 14 HVAC & Plumbing Rough-in | 30% | Available | TRUE | FALSE | Edward's LLC. | 2025-10-16 | West Star Bank | [7 empty] | 279950 | D/Beige | TRUE |  |  |  |  | Victor Jimenez
13804 | Summer Hail | 1592 | Berlin II | Summer Sky North U-2 Ph.1 | 21 | 43 | 38 Building Final / COO | 100% | Available | TRUE | FALSE | Edward's LLC. | 2025-07-22 | West Star Bank | [7 empty] | 300950 | B/Greige | TRUE |  |  |  | 2025-10-17 | Victor Jimenez
1449 | Summer Storm | 1721 | Tokyo | Summer Sky North U-2 Ph.1 | 14 | 64 | 38 Building Final / COO | 100% | Available | TRUE | FALSE | Edward's LLC. | 2025-07-22 | West Star Bank | [7 empty] | 307950 | C/Gray | TRUE |  |  |  | 2025-10-28 | Victor Jimenez
13800 | Summer Wave | 1721 | Tokyo | Summer Sky North U-2 Ph.1 | 20 | 64 | 38 Building Final / COO | 100% | BOM | TRUE | TRUE | Edward's LLC. | 2025-07-22 | West Star Bank | RMMC | FHA | Carlos Caballero/Luz Martinez | 2025-10-30 | 2025-11-26 | EH | 915-330-3450 | 307950 | D/Beige | TRUE | Pauline Barrio | Daisy Moreno | Cassandra Vasquez | 2025-10-28 | Victor Jimenez
13805 | Summer Wave | 1522 | Ayde T | Summer Sky North U-2 Ph.1 | 9 | 69 | 38 Building Final / COO | 100% | Available | TRUE | FALSE | Edward's LLC. | 2025-07-22 | West Star Bank | [7 empty] | 279950 | B/Greige | TRUE |  |  |  | 2025-11-18 | Victor Jimenez
13813 | Summer Wave | 1527 | Carmella T | Summer Sky North U-2 Ph.1 | 11 | 69 | 36 Final Paint | 90% | Available | TRUE | FALSE | Edward's LLC. | 2025-08-04 | West Star Bank | [7 empty] | 279950 | C/Gray | TRUE |  |  |  |  | Victor Jimenez
13817 | Summer Wave | 1658 | Denver | Summer Sky North U-2 Ph.1 | 12 | 69 | 32 Electrical/Plumbing/HVAC Finals | 80% | Available | TRUE | FALSE | Edward's LLC. | 2025-08-04 | West Star Bank | [7 empty] | 302950 | D/Beige | TRUE |  |  |  |  | Victor Jimenez
13901 | Thunder Sky | 1522 | Ayde T | Summer Sky North U-2 Ph.1 | 1 | 71 | 32 Electrical/Plumbing/HVAC Finals | 80% | Available | TRUE | FALSE | Edward's LLC. | 2025-08-04 | West Star Bank | [7 empty] | 282950 | C/Gray | TRUE |  |  |  |  | Victor Jimenez
13905 | Thunder Sky | 1583 | Karla T | Summer Sky North U-2 Ph.1 | 2 | 71 | 32 Electrical/Plumbing/HVAC Finals | 80% | Available | TRUE | FALSE | Edward's LLC. | 2025-08-04 | West Star Bank | [7 empty] | 279950 | B/Greige | TRUE |  |  |  |  | Victor Jimenez
13904 | Summer Wave | 1721 | Tokyo | Summer Sky North U-2 Ph.1 | 17 | 71 | 32 Electrical/Plumbing/HVAC Finals | 80% | Available | TRUE | FALSE | Edward's LLC. | 2025-08-04 | West Star Bank | [7 empty] | 304950 | B/Greige | TRUE |  |  |  |  | Victor Jimenez
14565 | John Mcneely | 1920 | Lillian II F (PT) | TDE U-89 | 6 | 619 | 38 Building Final / COO | 100% | Sold | TRUE | TRUE | Edward's LLC. | 2025-03-07 | TRX | RMMC | VA | Armando Campos | 2025-10-27 | 2025-12-05 | EH | 626-536-8018 | 379950 | Done | TRUE | Sandie Aguilar | Julie Loving-Scott | Michelle Beltran | 2025-10-09 | Samuel Velasco
15248 | Gauge | 1527 | Carmella | TDE U-90 | 13 | 8 | 40 Ready for Walk-Through | 100% | Model | TRUE | FALSE | Edward's LLC. | 2024-05-31 | RMMC | [7 empty] | 264950 | B/Gray | TRUE |  |  |  | 2024-08-16 | Juan Luna
15040 | Destination | 1522 | Ayde T | TDE U-91 | 21 | 37 | 40 Ready for Walk-Through | 100% | Available | TRUE | FALSE | Edward's LLC. | 2025-06-05 | RMMC | [7 empty] | 274950 | B/Greige | TRUE |  |  |  | 2025-09-12 | Juan Luna
3841 | Peak | 1495 | Yoli T | TDE U-91 | 31 | 37 | 38 Building Final / COO | 100% | Sold | TRUE | TRUE | Edward's LLC. | 2025-06-16 | RMMC | RMMC | FHA | German Berumen/Julia Trancoso | 2025-11-26 | 2025-12-16 | EH | 915-838-5112 | 274950 | A/Beige | TRUE | Ceci Estrada | Team Edgar Barrio/Mark Morales | Team Edgar Barrio/Mark Morales | 2025-09-11 | Ismael Salazar
15065 | Destination | 1522 | Ayde T | TDE U-91 | 1 | 38 | 40 Ready for Walk-Through | 100% | Sold | TRUE | TRUE | Edward's LLC. | 2025-06-30 | RMMC | Change Home Mortgage | FHA | Cristal Vega | 2025-11-21 | 2025-12-12 | EH | 915-777-6649 | 277950 | D/Gray | TRUE | Patrick Guerra | Rene Botello | Michelle Botello | 2025-09-24 | Juan Luna
15057 | Destination | 1450 | Mariel T | TDE U-91 | 3 | 38 | 38 Building Final / COO | 100% | Sold | TRUE | TRUE | Edward's LLC. | 2025-06-30 | RMMC | Change Home Mortgage | FHA | Julian Belmontes | 2025-11-25 | 2025-12-15 | EH | 915-525-1305 | 274950 | A/Beige | TRUE | Rocio Acosta | Team Home Guide/Bryan Rodriguez | Michelle Botello | 2025-10-01 | Juan Luna
15049 | Destination | 1522 | Ayde T | TDE U-91 | 5 | 38 | 38 Building Final / COO | 100% | Available | TRUE | FALSE | Edward's LLC. | 2025-06-30 | RMMC | [7 empty] | 274950 | B/Greige | TRUE |  |  |  | 2025-11-18 | Juan Luna
15041 | Destination | 1450 | Mariel T | TDE U-91 | 7 | 38 | 38 Building Final / COO | 100% | Sold | TRUE | TRUE | Edward's LLC. | 2025-07-16 | RMMC | Change Home Mortgage | FHA | Rene Barrera/Caballero | 2025-11-25 | 2025-12-26 | EH | 915-843-9340 | 274950 | C/Gray | TRUE | Patrick Guerra | Rocio Orozco | Diana Romero | 2025-11-18 | Juan Luna
15033 | Destination | 1522 | Ayde T | TDE U-91 | 9 | 38 | 38 Building Final / COO | 100% | Available | TRUE | FALSE | Edward's LLC. | 2025-07-16 | RMMC | [7 empty] | 274950 | A/Beige | TRUE |  |  |  | 2025-11-18 | Juan Luna
15025 | Destination | 1450 | Mariel T | TDE U-91 | 11 | 38 | 38 Building Final / COO | 100% | Sold | TRUE | TRUE | Edward's LLC. | 2025-07-16 | RMMC | RMMC | VA | Sonia McElfresh | 2025-11-20 | 2025-12-22 | EH | 951-476-4353 | 277950 | C/Gray | TRUE | Pauline Barrio | Team Edgar Garcia/Crystal Aguilera | Michelle Botello | 2025-11-20 | Juan Luna
15101 | Destination | 1527 | Carmella T | TDE U-91 | 19 | 39 | 35 Carpet | 90% | Sold | TRUE | TRUE | Edward's LLC. | 2025-08-28 | West Star Bank | RMMC | VA | Matthew Suthiart | 2025-10-08 | 2025-12-30 | EH | 337-465-3395 | 277950 | Done/Gray | TRUE | Pauline Barrio | Team Edgar Garcia/Jessica Gomez | Juan Pablo Amaya |  | Ismael Salazar
15105 | Destination | 1532 | Arely T | TDE U-91 | 18 | 39 | 32 Electrical/Plumbing/HVAC Finals | 80% | Available | TRUE | FALSE | Edward's LLC. | 2025-08-28 | West Star Bank | [7 empty] | 274950 | B/Beige | TRUE |  |  |  |  | Ismael Salazar
15109 | Destination | 1583 | Karla T | TDE U-91 | 17 | 39 | 28 Cabinets | 70% | Available | TRUE | FALSE | Edward's LLC. | 2025-08-28 | West Star Bank | [7 empty] | 274950 | C/Beige | TRUE |  |  |  |  | Ismael Salazar
15113 | Destination | 1522 | Ayde T | TDE U-91 | 16 | 39 | 28 Cabinets | 70% | Available | TRUE | FALSE | Edward's LLC. | 2025-08-28 | West Star Bank | [7 empty] | 274950 | A/Gray | TRUE |  |  |  |  | Ismael Salazar
15117 | Destination | 1527 | Carmella T | TDE U-91 | 15 | 39 | 28 Cabinets | 70% | Available | TRUE | FALSE | Edward's LLC. | 2025-08-21 | West Star Bank | [7 empty] | 274950 | B/Beige | TRUE |  |  |  |  | Ismael Salazar
15121 | Destination | 1450 | Mariel T | TDE U-91 | 14 | 39 | 28 Cabinets | 70% | Available | TRUE | FALSE | Edward's LLC. | 2025-08-21 | West Star Bank | [7 empty] | 274950 | C/Beige | TRUE |  |  |  |  | Ismael Salazar
15125 | Destination | 1583 | Karla T | TDE U-91 | 13 | 39 | 30 Paint 2 + Trim 2 + Stucco Paint | 75% | Available | TRUE | FALSE | Edward's LLC. | 2025-08-21 | West Star Bank | [7 empty] | 274950 | Done/Beige | TRUE |  |  |  |  | Ismael Salazar
15129 | Destination | 1522 | Ayde T | TDE U-91 | 12 | 39 | 32 Electrical/Plumbing/HVAC Finals | 80% | Available | TRUE | FALSE | Edward's LLC. | 2025-08-21 | West Star Bank | [7 empty] | 274950 | B/Beige | TRUE |  |  |  |  | Ismael Salazar
15133 | Destination | 1527 | Carmella T | TDE U-91 | 11 | 39 | 32 Electrical/Plumbing/HVAC Finals | 80% | Sold | TRUE | TRUE | Edward's LLC. | 2025-08-21 | West Star Bank | All Western Mtg. | FHA | Amy Moreno | 2025-11-25 | 2025-12-30 | EH | 915-777-5671 | 274950 | C/Beige | TRUE | Javier Parra | Stephanie Morales | Cassandra Vasquez |  | Ismael Salazar
15137 | Destination | 1450 | Mariel T | TDE U-91 | 10 | 39 | 32 Electrical/Plumbing/HVAC Finals | 80% | Available | TRUE | FALSE | Edward's LLC. | 2025-08-15 | West Star Bank | [7 empty] | 274950 | A/Gray | TRUE |  |  |  |  | Ismael Salazar
15141 | Destination | 1583 | Karla T | TDE U-91 | 9 | 39 | 32 Electrical/Plumbing/HVAC Finals | 80% | Pending | TRUE | FALSE | Edward's LLC. | 2025-08-15 | West Star Bank | [7 empty] | 274950 | B/Beige | TRUE |  |  |  |  | Ismael Salazar
15145 | Destination | 1522 | Ayde T | TDE U-91 | 8 | 39 | 35 Carpet | 90% | Available | TRUE | FALSE | Edward's LLC. | 2025-08-15 | West Star Bank | [7 empty] | 274950 | C/Beige | TRUE |  |  |  |  | Ismael Salazar
15149 | Destination | 1527 | Carmella T | TDE U-91 | 7 | 39 | 35 Carpet | 90% | Pending | TRUE | FALSE | Edward's LLC. | 2025-08-15 | West Star Bank | [7 empty] | 274950 | A/Gray | TRUE |  |  |  |  | Ismael Salazar
15153 | Destination | 1450 | Mariel T | TDE U-91 | 6 | 39 | 38 Building Final / COO | 100% | Available | TRUE | FALSE | Edward's LLC. | 2025-08-15 | West Star Bank | [7 empty] | 274950 | C/Beige | TRUE |  |  |  | 2025-11-24 | Ismael Salazar
15157 | Destination | 1583 | Karla T | TDE U-91 | 5 | 39 | 38 Building Final / COO | 100% | Sold | TRUE | TRUE | Edward's LLC. | 2025-08-05 | West Star Bank | RMMC | VA | Alberto Chavez | 2025-11-25 | 2025-12-22 | EH | 915-422-8373 | 274950 | B/Beige | TRUE | Lizzet Urbina | Miguel Madrid | Angel Almeida | 2025-11-24 | Ismael Salazar
15161 | Destination | 1522 | Ayde T | TDE U-91 | 4 | 39 | 38 Building Final / COO | 100% | Available | TRUE | FALSE | Edward's LLC. | 2025-08-05 | West Star Bank | [7 empty] | 274950 | A/Gray | TRUE |  |  |  | 2025-11-14 | Ismael Salazar
15169 | Destination | 1450 | Mariel T | TDE U-91 | 2 | 39 | 38 Building Final / COO | 100% | Available | TRUE | FALSE | Edward's LLC. | 2025-08-05 | West Star Bank | [7 empty] | 274950 | B/Beige | TRUE |  |  |  | 2025-11-11 | Ismael Salazar
15173 | Destination | 1583 | Karla T | TDE U-91 | 1 | 39 | 38 Building Final / COO | 100% | Pending | TRUE | FALSE | Edward's LLC. | 2025-08-05 | West Star Bank | [7 empty] | 277950 | A/Gray | TRUE |  |  |  | 2025-11-11 | Ismael Salazar
15100 | Laura | 1527 | Carmella | TDE U-91 | 20 | 39 | 38 Building Final / COO | 100% | Sold | TRUE | TRUE | Edward's LLC. | 2025-08-15 | West Star Bank | RMMC | VA | Carlos Hernandez/Muniz-Arocho | 2025-11-18 | 2025-12-16 | EH | 270-498-2338 | 277950 | A/Gray | TRUE | Ruth Guevara | Penny Moore | Juan Pablo Amaya | 2025-11-07 | Juan Luna
15104 | Laura | 1532 | Arely | TDE U-91 | 21 | 39 | 38 Building Final / COO | 100% | Sold | TRUE | TRUE | Edward's LLC. | 2025-08-15 | West Star Bank | RMMC | VA | Francisco Lujan | 2025-11-26 | 2025-12-26 | EH | 915-331-0237 | 274950 | B/Beige | TRUE | Lizzet Urbina | Laura Garrett | Carina Madrid-Gutierrez | 2025-11-18 | Juan Luna
15108 | Laura | 1583 | Karla | TDE U-91 | 22 | 39 | 38 Building Final / COO | 100% | Sold | TRUE | TRUE | Edward's LLC. | 2025-08-15 | West Star Bank | Tailored Lending | FHA | Nayeli Ciriza | 2025-10-27 | 2025-12-05 | EH | 915-539-6231 | 274950 | Done/Gray | TRUE | Ivan Gonzalez | Eder Gallardo | Diana Caballero | 2025-11-11 | Juan Luna
15112 | Laura | 1535 | Ayde | TDE U-91 | 23 | 39 | 38 Building Final / COO | 100% | Sold | TRUE | TRUE | Edward's LLC. | 2025-08-15 | West Star Bank | RMMC | FHA | Sergio Hernandez | 2025-11-19 | 2025-12-17 | TC | 612-803-3298 | 274950 | C/Beige | TRUE | Christopher Ramirez | Saul Hernandez | Fernanda Cereceres | 2025-11-26 | Juan Luna
15116 | Laura | 1527 | Carmella | TDE U-91 | 24 | 39 | 34 Detail Wall Texture | 85% | Available | TRUE | FALSE | Edward's LLC. | 2025-08-15 | West Star Bank | [7 empty] | 274950 | B/Beige | TRUE |  |  |  |  | Juan Luna
15120 | Laura | 1450 | Mariel T | TDE U-91 | 25 | 39 | 32 Electrical/Plumbing/HVAC Finals | 80% | Available | TRUE | FALSE | Edward's LLC. |  | West Star Bank | [7 empty] | 274950 | A/Gray | TRUE |  |  |  |  | Juan Luna
15124 | Laura | 1583 | Karla | TDE U-91 | 26 | 39 | 32 Electrical/Plumbing/HVAC Finals | 80% | Available | TRUE | FALSE | Edward's LLC. |  | West Star Bank | [7 empty] | 274950 | C/Beige | TRUE |  |  |  |  | Juan Luna
15128 | Laura | 1535 | Ayde | TDE U-91 | 27 | 39 | 32 Electrical/Plumbing/HVAC Finals | 80% | Available | TRUE | FALSE | Edward's LLC. |  | West Star Bank | [7 empty] | 274950 | A/Gray | TRUE |  |  |  |  | Juan Luna
15132 | Laura | 1527 | Carmella | TDE U-91 | 28 | 39 | 32 Electrical/Plumbing/HVAC Finals | 80% | Available | TRUE | FALSE | Edward's LLC. |  | West Star Bank | [7 empty] | 274950 | C/Beige | TRUE |  |  |  |  | Juan Luna
15136 | Laura | 1450 | Mariel T | TDE U-91 | 29 | 39 | 32 Electrical/Plumbing/HVAC Finals | 80% | Available | TRUE | FALSE | Edward's LLC. |  | West Star Bank | [7 empty] | 274950 | B/Beige | TRUE |  |  |  |  | Juan Luna
15140 | Laura | 1583 | Karla | TDE U-91 | 30 | 39 | 32 Electrical/Plumbing/HVAC Finals | 80% | Available | TRUE | FALSE | Edward's LLC. | 2025-09-24 | West Star Bank | [7 empty] | 274950 | A/Gray | TRUE |  |  |  |  | Juan Luna
15144 | Laura | 1535 | Ayde | TDE U-91 | 31 | 39 | 29 Countertops | 70% | Available | TRUE | FALSE | Edward's LLC. | 2025-09-24 | West Star Bank | [7 empty] | 274950 | B/Beige | TRUE |  |  |  |  | Juan Luna
15148 | Laura | 1527 | Carmella | TDE U-91 | 32 | 39 | 28 Cabinets | 70% | Available | TRUE | FALSE | Edward's LLC. | 2025-09-24 | West Star Bank | [7 empty] | 274950 | A/Gray | TRUE |  |  |  |  | Juan Luna
15152 | Laura | 1450 | Mariel T | TDE U-91 | 33 | 39 | 27 Trim & Doors | 65% | Available | TRUE | FALSE | Edward's LLC. | 2025-09-24 | West Star Bank | [7 empty] | 274950 | C/Beige | TRUE |  |  |  |  | Juan Luna
15156 | Laura | 1583 | Karla | TDE U-91 | 34 | 39 | 27 Trim & Doors | 65% | Available | TRUE | FALSE | Edward's LLC. | 2025-09-24 | West Star Bank | [7 empty] | 274950 | B/Beige | TRUE |  |  |  |  | Juan Luna
15160 | Laura | 1535 | Ayde | TDE U-91 | 35 | 39 | 26 Tile | 60% | Available | TRUE | FALSE | Edward's LLC. |  | West Star Bank | [7 empty] | 274950 | A/Gray | TRUE |  |  |  |  | Juan Luna
15164 | Laura | 1527 | Carmella | TDE U-91 | 36 | 39 | 25 Paint | 55% | Available | TRUE | FALSE | Edward's LLC. |  | West Star Bank | [7 empty] | 274950 | C/Beige | TRUE |  |  |  |  | Juan Luna
15168 | Laura | 1450 | Mariel T | TDE U-91 | 37 | 39 | 25 Paint | 55% | Available | TRUE | FALSE | Edward's LLC. |  | West Star Bank | [7 empty] | 274950 | B/Beige | TRUE |  |  |  |  | Juan Luna
15172 | Laura | 1583 | Karla | TDE U-91 | 38 | 39 | 25 Paint | 55% | Available | TRUE | FALSE | Edward's LLC. |  | West Star Bank | [7 empty] | 277950 | A/Gray | TRUE |  |  |  |  | Juan Luna
15173 | Target | 1522 | Ayde T | TDE U-91 | 1 | 40 | 20 Insulation | 40% | Available | TRUE | FALSE | Edward's LLC. |  | West Star Bank | [7 empty] | 277950 | A/Gray | FALSE |  |  |  |  | Juan Luna
15169 | Target | 1527 | Carmella T | TDE U-91 | 2 | 40 | 20 Insulation | 40% | Available | TRUE | FALSE | Edward's LLC. |  | West Star Bank | [7 empty] | 274950 | B/Beige | FALSE |  |  |  |  | Juan Luna
15165 | Target | 1583 | Karla T | TDE U-91 | 3 | 40 | 21 Sheetrock Install | 45% | Available | TRUE | FALSE | Edward's LLC. |  | West Star Bank | [7 empty] | 274950 | C/Greige | FALSE |  |  |  |  | Juan Luna
15161 | Target | 1450 | Mariel T | TDE U-91 | 4 | 40 | 23 Texture | 50% | Available | TRUE | FALSE | Edward's LLC. |  | West Star Bank | [7 empty] | 274950 | A/Gray | FALSE |  |  |  |  | Juan Luna
15157 | Target | 1522 | Ayde T | TDE U-91 | 5 | 40 | 25 Paint | 55% | Available | TRUE | FALSE | Edward's LLC. |  | West Star Bank | [7 empty] | 274950 | B/Beige | FALSE |  |  |  |  | Juan Luna
15152 | Destination | 1527 | Carmella T | TDE U-91 | 33 | 40 | 25 Paint | 55% | Available | TRUE | FALSE | Edward's LLC. | 2025-09-25 | West Star Bank | [7 empty] | 274950 | C/Beige | TRUE |  |  |  |  | Ismael Salazar
15156 | Destination | 1522 | Ayde T | TDE U-91 | 34 | 40 | 25 Paint | 55% | Available | TRUE | FALSE | Edward's LLC. | 2025-09-25 | West Star Bank | [7 empty] | 274950 | B/Beige | TRUE |  |  |  |  | Ismael Salazar
15160 | Destination | 1532 | Arely T | TDE U-91 | 35 | 40 | 25 Paint | 55% | Available | TRUE | FALSE | Edward's LLC. | 2025-09-25 | West Star Bank | [7 empty] | 274950 | C/Greige | TRUE |  |  |  |  | Ismael Salazar
15164 | Destination | 1583 | Karla T | TDE U-91 | 36 | 40 |  |  | Available | TRUE | FALSE | Edward's LLC. |  | West Star Bank | [7 empty] | 274950 | B/Beige | FALSE
15168 | Destination | 1527 | Carmella T | TDE U-91 | 37 | 40 | 25 Paint | 55% | Available | TRUE | FALSE | Edward's LLC. | 2025-09-25 | West Star Bank | [7 empty] | 274950 | A/Gray | TRUE |  |  |  |  | Ismael Salazar
15172 | Destination | 1522 | Ayde T | TDE U-91 | 38 | 40 |  |  | Available | TRUE | FALSE | Edward's LLC. |  | West Star Bank | [7 empty] | 277950 | C/Greige | FALSE
15024 | Function | 1583 | Karla T | TDE U-91 | 19 | 36 | 27 Trim & Doors | 65% | Pending | TRUE | FALSE | Edward's LLC. | 2025-09-16 | West Star Bank | [7 empty] | 277950 | A/Gray | TRUE |  |  |  |  | Ismael Salazar
15028 | Function | 1522 | Ayde T | TDE U-91 | 20 | 36 | 26 Tile | 60% | Available | TRUE | FALSE | Edward's LLC. | 2025-09-16 | West Star Bank | [7 empty] | 274950 | B/Beige | TRUE |  |  |  |  | Ismael Salazar
15032 | Function | 1450 | Mariel T | TDE U-91 | 21 | 36 | 25 Paint | 55% | Available | TRUE | FALSE | Edward's LLC. | 2025-09-16 | West Star Bank | [7 empty] | 274950 | C/Beige | TRUE |  |  |  |  | Ismael Salazar
15036 | Function | 1527 | Carmella T | TDE U-91 | 22 | 36 | 27 Trim & Doors | 65% | Available | TRUE | FALSE | Edward's LLC. | 2025-09-16 | West Star Bank | [7 empty] | 274950 | A/Gray | TRUE |  |  |  |  | Ismael Salazar
15040 | Function | 1522 | Ayde T | TDE U-91 | 23 | 36 | 27 Trim & Doors | 65% | Available | TRUE | FALSE | Edward's LLC. | 2025-09-16 | West Star Bank | [7 empty] | 277950 | C/Beige | TRUE |  |  |  |  | Ismael Salazar
3825 | Perspective | 1527 | Carmella | TDE U-91 | 8 | 36 | 38 Building Final / COO | 100% | Sold | TRUE | TRUE | Edward's LLC. | 2025-09-05 | West Star Bank | REV Mortgage | Conventional | Alberto Lujan | 2025-08-04 | 2025-11-21 | EH | 915-791-2252 | 277950 | Done/Beige | TRUE | Mayra Rojo | Eder Gallardo |  | 2025-11-17 | Ismael Salazar
3429 | Marbury | 1495 | RGV Yoli | The Heights on Trenton Phase II | 124 | 0 | 40 Ready for Walk-Through | 100% | Sold | TRUE | TRUE | Edward's RGV | 2024-12-12 | TRX | Cross Country Mortgage | FHA | Brittney Jasso | 2025-11-18 | 2025-12-15 | TC | 956-378-2801 | 270000 | Greyish | TRUE | Xavier Martinez | Renee Gonzalez |  | 2025-05-15 | Irving Gallardo
12333 | Ben Dowell Way | 1420 | Elena T | Tierra Del Norte | 14 | 2 | 38 Building Final / COO | 100% | Sold | TRUE | TRUE | Edward's LLC. | 2025-07-22 | West Star Bank | Veterans United | VA | Patrick Ruther | 2025-11-10 | 2025-12-08 | EH | 203-822-8654 | 269950 | F/Gray | TRUE | Shane Lamberson | Team Jacqueline Rodriguez/Jacqueline Rodriguez | Diana Romero | 2025-11-18 | Josue Hinojos
12329 | Ben Dowell Way | 1350 | Ivana T | Tierra Del Norte | 15 | 2 | 38 Building Final / COO | 100% | Available | TRUE | FALSE | Edward's LLC. | 2025-07-01 | West Star Bank | [7 empty] | 269950 | D/Gray | TRUE |  |  |  | 2025-11-07 | Josue Hinojos
12325 | Ben Dowell Way | 1400 | Emily T | Tierra Del Norte | 16 | 2 | 29 Countertops | 70% | Sold | TRUE | FALSE | Edward's LLC. | 2025-08-28 | West Star Bank | RMMC | VA | Marc Sarver | 2025-10-20 | 2026-01-13 |  | 915-217-3222 | 269950 | C/Beige | TRUE | Pauline Barrio | Orlando Sandoval | Audrey Gutierrez |  | Josue Hinojos
12321 | Ben Dowell Way | 1450 | Mariel T | Tierra Del Norte | 17 | 2 | 36 Final Paint | 90% | Sold | TRUE | TRUE | Edward's LLC. | 2025-08-05 | West Star Bank | Tru Rate Lending | Conventional | Jandaly Khatib | 2025-11-19 | 2025-12-23 | EH | 915-886-8332 | 269950 | B/Gray | TRUE | Brandon List | Mark Barrios | Cassandra Vasquez |  | Josue Hinojos
12317 | Ben Dowell Way | 1420 | Elena T | Tierra Del Norte | 18 | 2 | 36 Final Paint | 90% | Sold | TRUE | TRUE | Edward's LLC. | 2025-07-22 | West Star Bank | Veterans United | VA | Richard De Almeida Monteiro | 2025-10-30 | 2025-12-16 | EH | 973-735-4572 | 269950 | F/Gray | TRUE | Karlie Clark | Team Edgar Barrio/Mark Morales | Team Edgar Barrio/Mark Morales |  | Josue Hinojos
12313 | Ben Dowell Way | 1350 | Ivana T | Tierra Del Norte | 19 | 2 | 38 Building Final / COO | 100% | Available | TRUE | FALSE | Edward's LLC. | 2025-07-17 | West Star Bank | [7 empty] | 269950 | A/Beige | TRUE |  |  |  | 2025-11-07 | Josue Hinojos
12309 | Ben Dowell Way | 1400 | Emily T | Tierra Del Norte | 20 | 2 | 38 Building Final / COO | 100% | Pending | TRUE | FALSE | Edward's LLC. | 2025-07-22 | West Star Bank | [7 empty] | 269950 | B/Gray | TRUE |  |  |  | 2025-11-18 | Josue Hinojos
12305 | Ben Dowell Way | 1450 | Mariel T | Tierra Del Norte | 21 | 2 | 38 Building Final / COO | 100% | Sold | TRUE | TRUE | Edward's LLC. | 2025-07-22 | West Star Bank | RMMC | Conventional | Ian Laningham | 2025-11-03 | 2025-12-10 | EH | 623-418-0222 | 269950 | C/Beige | TRUE | Pauline Barrio | Team Edgar Barrio/Edgar Barrio | Team Edgar Barrio/Edgar Barrio | 2025-11-18 | Josue Hinojos
7300 | Fray Garcia Way | 1350 | Ivana T | Tierra Del Norte | 10 | 3 | 35 Carpet | 90% | Sold | TRUE | TRUE | Edward's LLC. | 2025-08-05 | West Star Bank | RMMC | FHA | Gerardo Ramirez/Alvarado | 2025-11-12 | 2025-12-15 | EH | 787-601-3680 | 272950 | A/Beige | TRUE | Michael Sanchez | Brenda Garcia | Marisol Dominguez |  | Josue Hinojos
7309 | John Gerald Way | 1450 | Mariel T | Tierra Del Norte | 11 | 3 | 36 Final Paint | 90% | Sold | TRUE | TRUE | Edward's LLC. | 2025-08-28 | West Star Bank | RMMC | FHA | Raul Diaz | 2025-07-22 | 2025-12-17 | EH | 915-691-4341 | 272950 | Done/Beige | TRUE | Pauline Barrio | Team Edgar Garcia/Jessica Garcia | Juan Pablo Amaya |  | Josue Hinojos
12300 | Jack Vowell Way | 1350 | Ivana T | Tierra Del Norte | 1 | 2 | 38 Building Final / COO | 100% | Sold | TRUE | TRUE | Edward's LLC. | 2025-08-28 | West Star Bank | Annie-Mac | FHA | Josue Hinojos | 2025-11-06 | 2025-11-26 | EH | 915-261-9531 | 272950 | Done | TRUE | Suzie Gallardo | Eder Gallardo |  | 2025-11-18 | Josue Hinojos
12301 | Ben Dowell Way | 1350 | Ivana T | Tierra Del Norte | 22 | 2 | 40 Ready for Walk-Through | 100% | Sold | TRUE | TRUE | Edward's LLC. | 2025-06-24 | West Star Bank | Neighbors Bank | VA | Manuele Ahsiu | 2025-11-10 | 2025-12-08 | EH | 808-221-7960 | 272950 | B/Gray | TRUE | Neil Hansen | Linda Bastraw | Michelle Beltran | 2025-09-23 | Josue Hinojos
7324 | Fray Garcia Way | 1450 | Mariel T | Tierra Del Norte | 4 | 3 | 26 Tile | 60% | Sold | TRUE | FALSE | Edward's LLC. | 2025-09-16 | West Star Bank | RMMC | VA | Isaiah Warren | 2025-09-12 | 2026-01-15 | EH | 757-892-9165 | 269950 | A/Beige | TRUE | Michael Sanchez | Jesse Loya | Edgar Barrio/Mark Morales |  | Josue Hinojos
7321 | John Gerald Way | 1350 | Ivana T | Tierra Del Norte | 14 | 3 | 38 Building Final / COO | 100% | Available | TRUE | FALSE | Edward's LLC. | 2025-07-22 | West Star Bank | [7 empty] | 269950 | F/Gray | TRUE |  |  |  | 2025-11-18 | Josue Hinojos
7329 | John Gerald Way | 1400 | Emily T | Tierra Del Norte | 16 | 3 | 38 Building Final / COO | 100% | Sold | TRUE | TRUE | Edward's LLC. | 2025-07-01 | West Star Bank | CLF Mortgage | FHA | Viviana Aguirre de la Ree | 2025-10-27 | 2025-11-25 | EH | 915-533-1122 | 269950 | A/beige | TRUE | Cory Balthaser | Hector Nevarez | Diana Caballero | 2025-10-01 | Josue Hinojos
7333 | John Gerald Way | 1450 | Mariel T | Tierra Del Norte | 17 | 3 | 38 Building Final / COO | 100% | Available | TRUE | FALSE | Edward's LLC. | 2025-07-17 | West Star Bank | [7 empty] | 269950 | D/Gray | TRUE |  |  |  | 2025-11-18 | Josue Hinojos
7337 | John Gerald Way | 1350 | Ivana T | Tierra Del Norte | 18 | 3 | 38 Building Final / COO | 100% | Sold | TRUE | TRUE | Edward's LLC. | 2025-07-01 | West Star Bank | First Community Mtg. | FHA | Hector Guijarro/Pasillas | 2025-11-05 | 2025-12-09 | EH | 661-699-3663 | 269950 | B/Gray | TRUE | David Rodriguez | Team Edgar Garcia/Denise Reyes | Juan Pablo Amaya | 2025-10-01 | Josue Hinojos
7341 | John Gerald Way | 1420 | Elena T | Tierra Del Norte | 19 | 3 | 38 Building Final / COO | 100% | Sold | TRUE | TRUE | Edward's LLC. | 2025-08-05 | West Star Bank | Cash | Cash | Alonso Aguilar | 2025-11-13 | 2025-11-26 | EH | 915-873-1067 | 269950 | F/Gray | TRUE |  | Team Edgar Barrio/Mark Morales | Team Edgar Barrio/Mark Morales | 2025-11-18 | Josue Hinojos
7300 | John Gerald Way | 1879 | Hailey | Tierra Del Norte | 26 | 5 | 27 Trim & Doors | 65% | Pending | TRUE | FALSE | Edward's LLC. | 2025-09-16 | West Star Bank | [7 empty] | 345950 | Gray | TRUE |  |  |  |  | Josue Hinojos